## Sheet1
AS9100 Implementation and Transition Plan
2013
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb
Identify Company Resources | bar: 2013 Jan
Research Outside Consultants | bar: 2013 Jan
Review Current Quality System | bar: 2013 Jan
Develop Process Structure | bar: 2013 Jan
Identify Record Retention Requirements | bar: 2013 Feb
Develop Procedures AS9100C | bar: 2013 Feb to 2013 Apr
Develop forms AS9100C | bar: 2013 Feb to 2013 Apr
Procedure Review and Approval | bar: 2013 Feb to 2013 Apr
Write Job Descriptions and Requirements | bar: 2013 Apr to 2013 Aug
Perform Training | bar: 2013 Mar to 2013 Aug
Implement QMS and generate records | bar: 2013 Apr to 2013 Nov
Contract registrar & set audit dates | bar: 2013 Jul
Perform Internal Audits | bar: 2013 Sep to 2013 Oct
Complete IA Observations and Findings | bar: 2013 Oct
Conduct Management Review | bar: 2013 Nov
Registrar Pre-Assessment | bar: 2013 Nov
Complete Observations and Findings | bar: 2013 Nov
ISO9001:2008/AS9100C Audit Stage 1 & 2 | bar: 2013 Nov
Recommended by auditor to be AS9100 certified
Planned
Complete
Behind, will Recover
Behind, will Not Recover