## Slide 2: Eagle Project Guide Red Bear ( David Bowery ) BsaEagleProject@Cox.net 918-857-3561 Cell 918-838-4238 Land BsaEagleProject.ORG

## Slide 4: 2021 Indian Nations Council SCOUTS BSA LIFE TO EAGLE SEMINAR
THE EAGLE SCOUT SERVICE PROJECT

## Slide 5: PURPOSE
WHAT IS THE
5
OF AN
EAGLE PROJECT?

## Slide 6: Purpose:
6
Help a Deserving Organization
Gain Useful Skills
Accomplish Something Important
DEMONSTRATE LEADERSHIP

## Slide 7: Requirement #5
7
A Scout Must:
Plan, Develop, and Give Leadership to others in a Service Project.
The Project Must be Helpful for a:
Religious Institution,
School, or
Community Organization

## Slide 8: Requirement #5
8
Scouts must use the BSA Eagle Scout Service Project Workbook.
The Project Proposal must be approved before any work is started.

## Slide 9: How to start?
9
Project Ideas:
  Build, Improve or Install something.
  Organize a Drive or Community Effort.
  The CBD Life to Eagle Guide (on-line) has many project ideas.
Benefiting Organizations:
  Find Organizations that have sponsored Eagle Projects.
  Ask what they need done.

## Slide 10: Looking for a Project?
10
Think about your interests and passions.
Is there a skill you want to learn?
Consider your school, your church, your community, local parks …
Talk to your Eagle Advisor and Scoutmaster.
Ask other Eagles!

## Slide 11: Acceptable Projects:
11
Require planning, development, demonstration of leadership.
Are feasible – Not too small, not too big.
Are safe for workers and the public.
Are beneficial and have a Project Beneficiary (religious, educational or community organization).

## Slide 12: Unacceptable Projects:
12
Pre-planned by the beneficiary, organized or lead by others.
Routine labor or maintenance.
Benefit BSA organizations or for- profit businesses.
Primarily fundraisers.
Lack required approvals.

## Slide 13: Obstacles to Success
10
Procrastination
Pessimism/Optimism
Confusion
Distractions
No schedule or timeline
No follow through
Failure to communicate

## Slide 14: Don’t Panic!
11

## Slide 15: The Project Workbook Publication No. 512-927 Jan. 2021

## Slide 16: The Workbook Publication No. 512-927 Jan. 2021
Fillable and Expandable PDF
Available online: BsaEagleProject.orgwww.scouting.org
Must read and use entire workbook

## Slide 17: Service Project Process
14
Propose
Plan
Do it
Report

## Slide 18: Clarifying Expectations
Important “Message to Scouts and Parents or Guardians”
Clarifies what Scouts are expected to do & what Scouts should expect from Adult Leaders
Page 4

## Slide 19: Notes on Risk Management (Page 5)
Eagle Projects are Scout activities subject to normal BSA policies and procedures.
Units must assure that projects are conducted safely and standard practices for Youth Protection and Two-Deep Leadership are followed.
The “Guide to Safe Scouting” applies.

## Slide 20: Track Your Time!
All time spent on your project should be tracked and reported!
Use a notebook or computer spreadsheet as a project diary. Record:
  Date, start and stop time, elapsed time and describe what you did.
Include:
  Time spent on research, discussions, phone calls, Workbook entries.
  Time spent preparing for and conducting the project.
  Time of others who are helping you.
It all counts as project time.

## Slide 21: Track Your Time!

## Slide 22: PROJECT PROPOSAL

## Slide 23: Proposal Page A Instructions for Completing Proposal
Note the Five Tests of an Acceptable Project
Must Read Carefully
Understand how to work with your Project Beneficiary
The Proposal is a First Step. The Project Plan is the Next Step
No project work until Proposal and Planning are complete

## Slide 24: Proposal Page B Contact Information
Your Info
Unit Info
Unit Leader
Committee Chair
Advancement Coordinator
Project Beneficiary
Beneficiary Rep.
Council Service Center
District Eagle Rep.
Project Coach
Information you will need as you develop your project.
20

## Slide 25: Proposal Page C
Project Description
Add Pictures, Drawings, Diagrams etc. (as separate document)
Describe Needs & Project Benefits
Start and End Dates

## Slide 26: Photographs
Photos are a great way to document your project.
Proposal photos show conditions before the project was done.
Assign someone to take photos of the project in progress.
Take photos after the project is complete.
Captions are very helpful!

## Slide 27: Proposal Page D
Giving Leadership – Work Crew and Challenges
Materials Needed
Supplies Needed

## Slide 28: Proposal Page E
Tools Needed
Permits & Permissions
Potential Other Needs

## Slide 29: Fundraising & Contributions
The project purpose may not be to raise funds (money).
Projects may collect donations (things) for a charitable purpose.
Fundraising is permitted to support your Eagle Project.
No approvals are required to raise less than $500.
There is no limit for fundraising or contributions from:
  The beneficiary
  The candidate’s family or relatives
  The candidate’s unit or chartered organization
  Parents or members of the candidate’s unit

## Slide 30: Proposal Page F
Prelim Cost Estimate (and Fundraising)
Project Phases (Include activities to prepare for the project)
Logistics (Transportation and coordination)

## Slide 31: Proposal Page G
Safety Issues and mitigation
Candidate’s Promise and Signature
Approval Signatures
Additional Detailed Planning

## Slide 32: Proposal Page G Candidate’s Promise
I have read this
“On my honor as a Scout,
entire workbook, including the "Message to Scouts and Parents or Guardians" on page 5. I promise to be the leader of this project, and to do my best to carry it out for the maximum benefit to the religious institution, school, or community I have chosen as beneficiary.”
Do not begin any work on your project, or raise
any money, or obtain any materials, until your
project proposal has been approved.

## Slide 33: Proposal Page G Approvals
Last

## Slide 34: Information for Project Beneficiaries
30
Project Restrictions and Limitations
Approving Project Proposal and Scheduling
Approving the Project Plan
Supervision and Safety
Project Completion and Approval

## Slide 35: Fundraising Application Pages A & B
Form must be completed if more than $500 is to be raised from “outside” sources.
Donations of goods or materials do not require this form.

## Slide 36
PROJECT PLAN

## Slide 37: The Workbook States:
“A Scout who is prepared will complete the project plan, and then review it with the designated project coach before carrying out the project.”
“This can also improve your chances of passing the Eagle Scout board of review.”

## Slide 38: Mike Tyson once said…
“Everyone has a plan until they get punched in the mouth…”
What does that mean?
In life, unexpected things happen. A good plan anticipates difficulties and has contingency options.

## Slide 39: What is Planning?
5 P’s: Proper Planning Prevents Pitiful Performance.
What could go wrong? How will you make sure it doesn’t happen?
Who will do what – step by step.
Provide sufficient detail so that:
  You and the beneficiary understand how and what things will be done.
  You can explain it to everyone.
  Your project will be successful.

## Slide 40: Project Plan Page A
Project Description and Benefit – Changes from the proposal
Present Conditions or Situation - What will be changed by the project?
Comments from your proposal review
Explain impact of any changes
Completed following Proposal Approval

## Slide 41: Project Plan Page B
Project Phases – Sequence details
Work Processes Step by Step
Attachments (Lists, diagrams, maps, drawings, photos, project
documents, etc.}
Permits and Permissions

## Slide 42: Project Plan Page C
Materials Itemized with costs and
provider
Supplies Itemized with costs and
provider
Tools Itemized with costs, provider & operator
Other Needs Items or conditions

## Slide 43: Project Plan Page D
Giving Leadership
Staffing by task - Who will do what?
Describe your “Leadership Team”
Your “Training Plan”
Your “Communication Plan”
Logistics
Transporting workers
Transporting materials
Expenses & Revenue Totals by type

## Slide 44: Project Plan Page E
Logistics
Tool use and safety
Work Schedules
Food and restrooms
Safety
Potential hazards and proposed mitigation
Safety communication
Safety equipment
Safety briefings
Emergency access
40

## Slide 45: Project Plan Page E
Contingency Plans What if…
Review Comments From Your Coach

## Slide 46: Beneficiary Review
The Workbook states:
“You should … show your project plan to your beneficiary prior to carrying out your project.”
“Remember, the project beneficiary has the authority to require and approve a project plan.”

## Slide 47: Project Changes
Many projects require some changes from the approved Proposal.
Changes could include improvements.
If a major change is necessary, notify the Proposal approvers. Re-approval may be necessary.
43
GTA Para 9.0.2.7; page 65

## Slide 48
PROJECT REPORT

## Slide 49: Project Leadership
The Eagle candidate must be the project leader.
Others must be involved so you can demonstrate leadership.
Don’t permit adults to highjack your project. They should direct their suggestions to you for consideration.

## Slide 50: Completing The Project
Complete the Project Report ASAP – while your memory is fresh.
The Candidate and Beneficiary must agree that the work is complete.
The completion date will be entered on your Eagle Scout Rank Application (ESRA)

## Slide 51: Project Report Page A
Project Description
What was actually done
Describe your planning process
Observations
What went well?
What challenges were encountered?
Changes
Positive, neutral, negative
Project Execution

## Slide 52: Project Report Page B
Leadership:
Demonsatrated?
What was: Most Difficult?
Most Rewarding?
What did you learn?
Materials, Supplies, &Tools
Too much? Too little?
Service Project Data:
Number of workers
Hours worked

## Slide 53: Project Report Page C
Funding
Funds and materials collected
Sufficient?
Excess?
Acknowledgments?
Attach Photos and Other Project Documents
Candidate’s Promise
Completion Approvals
Beneficiary
Unit Leader

## Slide 54: Project Report Page C
Scout
Beneficiary
Unit Leader
Sign and date before you seek other approvals.
50

## Slide 55: Final Project Approval
Members of your Eagle Board of Review will decide if the project was completed properly.
Be prepared to discuss:
  How you demonstrate leadership.
  How you directed others to accomplish the work.
  What benefits were achieved.
  What changes were necessary and why.

## Slide 56: Questions?

## Slide 58
trappers rendezvous
Quivira Council