EAST RANGE WATER BOARD

Monthly Meeting Minutes

Wednesday, June 12, 2024 4:30 P.M.

City/Town Government Center

Appointed Board Members for City of Aurora:   Douglas Gregor, Chairman of the Board; David Skelton; Dennis Schubbe;

Appointed Board Members for the Town of White:  Jon Skelton, Vice Chairman of the Board; Clark Niemi;

Absent Board Members:

Others Present:  Jodi Knaus (TOW); Kimberly Berens (COA); Richard Hess (COA Councilor); Jim Gentilini (COA); Joshua Stier (Bolton-Menk (Zoom)); Brian Guldan (Bolten-Menk (Zoom)); Robert Rutka;

1.  A board meeting was called to order by Chairman Gregor at 4:30 P.M.

2.  Consent Agenda:

- Approval of May 15, 2024 Regular Meeting Minutes & Special Meeting Minutes of May 30, 2024

- Treasurer’s Report – Interim Financing:  $143,681.57; Biwabik Fund:  $72,132.56; Total: $215,814.13

- Correspondence – Copy of letter sent to Magney Construction

- Approval of Disbursements:

- Bolton & Menk - $117,844.00 to be paid out of IRRR funds

- Utility Systems of America - $687,593.28; paid out of EPA funds & IRRR FUNDS

- Fryberger Law Firm - $3,359.51

- Fryberger Law Firm – $634.50

IT WAS MOVED BY JON SKELTON, SUPPORTED BY DENNIS SCHUBBE APPROVING THE CONSENT AGENDA AS PRESENTED AND DISCUSSED.  MOTION CARRIED

3.  Legal matters – Updates including but not limited to:

  - Scenic Acres – No pending legal matters

  - Creation of New Legal Entity Timeline & Guidance – involve Hoyt Lakes in discussion

- Guests – Robert Rutka presented to the Board the cleared area & removal of trees on the side of the roadway would be a perfect opportunity to build a bike path/walkway for citizens.  Jon Skelton directed Knaus to put on the Township agenda and Strategic Plan as it is a great idea.

- Construction Management Updates – Bolton & Menk – June 2024 Status Report

  - Funding Initiatives & Cumulative Accounting

- Interim Financing Allonge was approved to July 1, 2025 and copies were included in Board packet for review.

  - Engineering Work – Josh & Brian updated the Water Board on the status of Project and reviewed the schedule.

- Construction Updates – mobilization for water plant begins next week with Magney; trees are cleared in Scenic; permit was submitted for crossing the lake; Pineville lines are in and tested – waiting for results; Piping not used in Project under Change Order #2 is at the Aurora Public Works garage to be used for the Aurora Economic Development Project and bought by City of Aurora; David Skelton wants to see accountability of pipe swapping with City of Aurora Project and how that affects the Water Project costs – the pipe was paid for by the water project in which the contractor owns and sold to Aurora; this needs to be transparent so everyone understands the financials of the transaction and it should be clear in the documents.

2.)   Project Labor Agreement with Magney Status – Three contractors cannot comply with the PLA –

plumber, caulking, and fencer causing a $181,000 cost increase to the PLA.  Change order will be coming.  Meeting needs to be held with the Union prior to construction beginning.

IT WAS MOVED BY DAVID SKELTON, SUPPORTED BY JON SKELTON APPROVING A CHANGE ORDER AS AN INCREASE TO THE CONTRACT COST WITH MAGNEY CONSTRUCTION.  MOTION CARRIED

3.) Barr Engineering Sensitivity Results – DNR has not signed off yet; original plans were conservative; there is a safety factor as we want to make sure we are at the right depth level – Jacob Crispo is managing this and a meeting with Erika will be scheduled.

c.  Permitting & other Pending Items –

1.)  Appropriations Permit – pending

2.)  Contingency Agreement – pending

6. Community Outreach – Plan ribbon cutting event for August 21, 2024 at water plant as part of the regular meeting

7.  Other Business:

a.) St. James Pit & current water plant updates – lots of rain!

8.) Next Meeting Date: Wednesday, July 17, 2024 4:30 p.m.

9.) Adjournment

MOVED BY CLARK NIEMI, SUPPORTED BY DENNIS SCHUBBE TO ADJOURN AT 5:13 PM. MOTION CARRIED

Respectfully submitted,

Jodi Knaus, Administrative Recorder