## Stakeholders
Stakeholder Analysis
Stakeholder | Organigaztion | Stakeholder Name | Stake in Project | Power / Influence | Interest | Cost | Stakeholder Priority Network Index | What do we need from them? | Perceived Attitudes / Risks | Risk If They Are Not Engaged | Stakeholder Management Strategy | Responsibility | Date Last Revised | % | Cummlative %
1 | ACME Inc | Mr. Marvelous | Supplies Rockets | 5 | 9 | 7 | 315 | Rocket Motors | Wrong Rocket for Orbit | Receive Bad Press | Keep Informed | Mr. Sharkey | 2015-10-15 | 26.9% | 26.9%
2 | Launches, Inc | Ms. Wonderful | Manages Launch Pad | 7 | 10 | 4 | 280 | Launch Pad | Wrong Sequence of Launch | Receive Bad Press | Keep Informed | Mr. Sharkey | 2015-10-15 | 23.91% | 50.81%
3 | Assembly, Inc | Mr. Rabbit | Manages Rocket Assembly | 8 | 9 | 8 | 576 | Assembeled Sattelittes to Rocket Motors | Wrong Rocket or Sattlette Configurations | Receive Bad Press | Keep Informed | Mr. Sharkey | 2015-10-15 | 49.19% | 100%
4 | [6 empty] | 0 | [6 empty] | 0% | 100%
5 | [6 empty] | 0 | [6 empty] | 0% | 100%
6 | [6 empty] | 0 | [6 empty] | 0% | 100%
7 | [6 empty] | 0 | [6 empty] | 0% | 100%
8 | [6 empty] | 0 | [6 empty] | 0% | 100%
9 | [6 empty] | 0 | [6 empty] | 0% | 100%
10 | [6 empty] | 0 | [6 empty] | 0% | 100%

## Scales
Power / Influence Ratings |  | Interest Ratings |  | Cost Ratings
Rating | Criteria | Rating | Criteria | Rating | Criteria
10 | Extreme Power / Influence over Programs / Projects. | 10 | Extreme Interest in Programs / Projects. | 10 | Extereme Cost - X<5000000
9 | Very High Power / Influence over Programs / Projects. | 9 | Very High Interest in Programs / Projects. | 9 | Very High Cost - 1000000>X<5000000
8 | High Power / Influence over Programs / Projects. | 8 | High Interest in Programs / Projects. | 8 | High Cost - 750000>X<1000000
7 | Moderate Power / Influence over Programs / Projects. | 7 | Moderate Interest in Programs / Projects. | 7 | Moderate Cost - 250000>X<750000
6 | Medium High Power / Influence over Programs / Projects. | 6 | Medium High Interest in Programs / Projects. | 6 | Medium High Cost - 50000>X<250000
5 | Medium Low Power / Influence over Programs / Projects. | 5 | Medium Low Interest in Programs / Projects. | 5 | Medium Low Cost - 20000>X<50000
4 | Low Power / Influecnce over Programs / Projects. | 4 | Low Interest in Programs / Projects. | 4 | Low Cost - 10000>X<20000
3 | Very Low Power / Influence over Programs / Projects. | 3 | Very Low Interest in Programs / Projects. | 3 | Very Low Cost - 5000>X<10000
2 | Minor Power / Influence over Programs / Projects. | 2 | Minor Interest in Programs / Projects. | 2 | Minor Cost - 1000>X<5000
1 | No Power / Influence over Programs / Projects. | 1 | No Interest in Programs / Projects. | 1 | No Cost - <1000

## Stakeholder Analysis
Stakeholder Analysis
Stakeholder | Impact | Importance | Allegiance | AIH | LIH | HIH | MIH | Concerns | Actions
Mr. Marvelous
Ms. Wonderful
Mr. Rabbit
0
0
0
0
0
0
0
Key: AIH: Against It Happening LIH: Let It Happen HIH: Help It Happen MIH: Make It Happen

## Stakeholder Allegiance (hidden)
MARCORSYSCOM Stakeholder Allegiance
Assessment | Definition | How to Manage
Advocates | • Only group driving the change or project • Active communications, keep regularly involved | • ‘Internal’ champions and sponsorship • Input to key milestones and decisions • Use for internal promotion of objectives and benefits
Followers | • Have a low understanding of project aims and objectives • Increase their understanding for future benefit | • Support the project and tend to “go with the flow” • Keep informed and positive • Avoid the temptation to exploit
Indifferent | • Individual or groups yet to take a definitive position on the project • Identify gaps in knowledge and seek to fill them | • Seek their views on key issue and address concerns • Have a medium understanding and medium agreement • Be careful not to make them opponents
Blockers | Shows resistance to the project or its aims. Principally due to having a low understanding and low agreement. This can be driven by: • Proactive communication • Interview and meet • Explain and overcome fears | • Use conflict management techniques • A lack of communication • Seeks views once understanding starts to develop • A (perceived or actual) loss from project • Knowledge of error in project assumptions
Opponents | • Has high understanding but low agreement to the project • Initiate discussions and understand reasons for low acceptance | • Will potentially ‘lose out’ in some way from the activity • If the loss is perceived but not real, then convert using facts and data • Counter the reasons for low acceptance

## Stakeholder Analysis Map
Quadrant Alignments | [6 empty] | Quadrant Level
| 0 | 3 | 3 | 7 | 7 | 10 |  | X | Y
| 0 | 300 | 300 | 700 | 700 | 1000 | Min | 0 | 0
Bottom | 0 | 0 | 0 | 0 | 0 | 0 | One | 3 | 3
Low Left | 3 | 3 | 0 | 0 | 0 | 0 | Two | 7 | 7
Low Mid | 0 | 0 | 3 | 3 | 0 | 0 | Max | 10 | 10
Low Right | 0 | 0 | 0 | 0 | 3 | 3
Mid Left | 4 | 4 | 0 | 0 | 0 | 0
Mid Mid | 0 | 0 | 4 | 4 | 0 | 0
Mid Right | 0 | 0 | 0 | 0 | 4 | 4
Top Left | 3 | 3 | 0 | 0 | 0 | 0
Top Mid | 0 | 0 | 3 | 3 | 0 | 0
Top Right | 0 | 0 | 0 | 0 | 3 | 3