Hampden County Health Coalition-Holyoke Regional EDS Functional Drill

SNS Planning Elements

Emergency Dispensing Site (EDS) Functional Drill

Situation Manual(SitMan)

Hampden County Health Coalition-Holyoke Functional Emergency Dispensing Site Drill

DRAFT

Preface

Hampden County Health Coalition -Holyoke EDS Functional Drill is sponsored by Hampden County Health Coalition. This Situation Manual (SitMan) was produced with input, advice, and assistance from the Hampden County Health Coalition -Holyoke EDS Functional Drill] exercise planning team, which followed the guidance set forth in the Federal Emergency Management Agency (FEMA), Homeland Security Exercise and Evaluation Program (HSEEP).

The Hampden County Health Coalition -Holyoke EDS Functional Drill Situation Manual (SitMan) provides exercise participants with all the necessary tools for their roles in the exercise. This SitMan was developed with the advice and assistance of the members of the Hampden County Health Coalition -Holyoke EDS Functional Drill planning team. It is tangible evidence of Hampden County Health Coalition’s commitment to ensure public safety through collaborative partnerships that will prepare it to respond to any emergency.

The Hampden County Health Coalition -Holyoke EDS Functional Drill is an unclassified exercise. The control of information is based more on public sensitivity regarding the nature of the exercise than on the actual exercise content. Some exercise material is intended for the exclusive use of exercise planners, facilitators, and evaluators, but players may view other materials deemed necessary to their performance. The SitMan may be viewed by all exercise participants.

All exercise participants should use appropriate guidelines to ensure the proper control of information within their areas of expertise and to protect this material in accordance with current jurisdictional directives. Public release of exercise materials to third parties is at the discretion of Hampden County Health Coalition-Holyoke EDS Functional Drill exercise planning team.

This page is intentionally left blank.

# Handling Instructions

1.	The title of this document is Hampden County Health Coalition HCHC-Holyoke Emergency  Dispensing Site Functional Drill  Situation Manual (SitMan).

2.	The information gathered in this SitMan is For Official Use Only (FOUO) and should be handled as sensitive information not to be disclosed. This document should be safeguarded, handled, transmitted, and stored in accordance with appropriate security directives. Reproduction of this document, in whole or in part, without prior approval from Hampden County Health Coalition is prohibited.

3.	At a minimum, the attached materials will be disseminated only on a need-to-know basis and when unattended, will be stored in a locked container or area offering sufficient protection against theft, compromise, inadvertent access, and unauthorized disclosure.

4.	For more information, please consult the following points of contact (POCs):

Agency POC:

Hamden County Health Coalition

Pioneer Valley Planning Commission

60 Congress St, Springfield, MA 01104

Phone: (413) 781-6045

http://www.pvpc.org/

Exercise Director:

Liisa Jackson HSEEP Exercise Planner and Facilitator

Preparedness Specialty Services

8 Cross Street

Hopkinton, MA 01748\

#774-278-0050

http://www.preparednessspecialtyservices.org/

This page is intentionally left blank.

Contents

Handling Instructions	iii

Introduction	1

Background	1

Purpose	1

Scope	1

Target Capabilities	2

Exercise Objectives	2

Participants	3

Exercise Structure	3

Exercise Guidelines	3

Assumptions	4

Stage 1: Detection and Activation	5

Key Issues	6

Stage 2: Site Activation	7

Summary of Casualties	7

Key Issues	7

Stage 3: EDS Operations

Summary of Casualties……………………………………………...…………………………….8

Key Issues………………………………………………………   ……………………………….8

Stage 3: EDS Operations	9

Summary of Casualties	9

Key Issues	9

Appendix A: Agent Summary-Bacillus Anthracis	A-1

Appendix B: Acronym & Abbreviation List	B-1

Appendix C: Key Terminology	C-1

This page is intentionally left blank.

# Introduction

## Background

## We do not know if or when another anthrax attack might occur. However, federal agencies have worked for years with health departments across the country to plan and prepare for an anthrax attack. If such an emergency were to occur in the United States, CDC and other federal agencies would work closely with local and state partners to coordinate a response.

If a bioterrorist attack were to happen, Bacillus anthracis, the bacteria that causes anthrax, would be one of the biological agents most likely to be used. Biological agents are germs that can sicken or kill people, livestock, or crops. Anthrax is one of the most likely agents to be used because:

- Anthrax spores are easily found in nature, can be produced in a lab, and can last for a long time in the environment.

- Anthrax makes a good weapon because it can be released quietly and without anyone knowing. The microscopic spores could be put into powders, sprays, food, and water. Because they are so small, you may not be able to see, smell, or taste them.

- Anthrax has been used as a weapon before.

Anthrax has been used as a weapon around the world for nearly a century. In 2001, powdered anthrax spores were deliberately put into letters that were mailed through the U.S. postal system. Twenty-two people, including 12 mail handlers, got anthrax, and five of these 22 people died.

## Purpose

The purpose of this exercise is to provide participants an opportunity to evaluate current response concepts, plans, and capabilities for a response to a bioterrorism event in Hamden County Health Coalition. The exercise will focus on local emergency responder command and control coordination, critical decisions, notifications, and the integration of State and Federal assets necessary to save lives and protect public health and safety.

## Scope

This exercise will focus on the role of Hamden County Health Coalition members in response to the potential consequences of a bioterrorist event. Processes and decision-making are more important than last minute details. The emphasis is on coordination, integration of capabilities, problem identification, and resolution.

## Target Capabilities

The National Planning Scenarios and the establishment of the National Preparedness Priorities have steered the focus of homeland security toward a capabilities-based planning approach. Capabilities-based planning focuses on planning under uncertainty, since the next danger or disaster can never be forecast with complete accuracy. Therefore, capabilities-based planning takes an all-hazards approach to planning and preparation which builds capabilities that can be applied to a wide variety of incidents. States and Urban Areas use capabilities-based planning to identify a baseline assessment of their homeland security efforts by comparing their current capabilities against the Target Capabilities List (TCL) and the critical tasks of the Universal Task List (UTL). This approach identifies gaps in current capabilities and focuses efforts on identifying and developing priority capabilities and tasks for the jurisdiction. These priority capabilities are articulated in the jurisdiction’s homeland security strategy and Multi-Year Training and Exercise Plan, of which this exercise is a component of.

The capabilities listed below have been selected by the HCHC-Holyoke Functional EDS Exercise planning team from the priority capabilities identified in Hamden County Health Coalition ’s Multi-Year Training and Exercise Plan. These capabilities provide the foundation for development of the exercise objectives and scenario, as the purpose of this exercise is to measure and validate performance of these capabilities and their associated critical tasks.

Target Capabilities https://www.llis.dhs.gov.

- Capability # 8 Medical Counter Measures

- Capability # 15 Volunteer Management

## Exercise Objectives

Exercise design objectives are focused on improving understanding of a response concept, identifying opportunities or problems, and/or achieving a change in attitude.

Drill Objectives

- EDS Site Activation

- EDS Staff Activation and Volunteer Management

- EDS Medical Counter Measures

- EDS Demobilization

## Participants

- Players respond to the situation presented based on expert knowledge of response procedures, current plans and procedures, and insights derived from training.

- Observers support the group in developing responses to the situation during the discussion; however, they are not participants in the moderated discussion period.

- Facilitators provide situation updates and moderate discussions. They also provide additional information or resolve questions as required. Key planning committee members may also assist with facilitation as subject matter experts (SMEs) during the tabletop exercise.

- Evaluators use Exercise Evaluation Guides (EEGs) and other evaluation tools to assess and document participants’ performance against established emergency plans and exercise evaluation criteria, in accordance with HSEEP standards. Evaluators are typically chosen from amongst planning committee members or the agencies/organizations that are participating in the exercise.

Exercise Structure

- Stage 1: Detection and Activation

- Stage 2: Response Underway

- Stage 3: On-going Operations

- Stage 4: Demobilization

Exercise guidelines

- This is an open, low-stress, no-fault environment. Varying viewpoints, even disagreements, are expected.

- Respond based on your knowledge of current plans and capabilities (i.e., you may use only existing assets) and insights derived from training.

- Decisions are not precedent setting and may not reflect your organization’s final position on a given issue. This is an opportunity to discuss and present multiple options and possible solutions.

- Issue identification is not as valuable as suggestions and recommended actions that could improve response and preparedness efforts. Problem-solving efforts should be the focus.

Assumptions

In any exercise a number of assumptions may be necessary to complete play in the time allotted. During this exercise, the following apply:

- The scenario is plausible, and events occur as they are presented.

- There is no “hidden agenda”, nor any trick questions.

- All players receive information at the same time.

# Stage 1: Detection and Activation

### February 9, 2017, 10:00AM

After a recent resurgence in terrorist activity in the Middle East, credible intelligence at home and abroad has projected the possibility of a terrorist attack on U.S. soil.  Over the course of recent months successful terrorist attacks have taken place in Mumbai, India and St. Petersburg, Russia.  During a raid on a terrorist safe house in London, materials used to cultivate biological weapons were seized.  Intelligence and Health Care Communities have heightened awareness and surveillance measures. Reliable intelligence points to the possible formation of an active terrorist cell posing a direct threat to the city of Holyoke, MA and surrounding communities.

### February 9, 2017

CERT team and EDS Site Staff stage all of the chairs, tables, signage and other supplies needed for the EDS.

### February 10, 2017, 7:30AM

A white powder incident at Holyoke Community College is confirmed by the State Lab as Anthrax.  Mass prophylaxis is needed to treat those exposed within 48 hours. The City of Holyoke has put EDS Staff and volunteers are on stand-by to open the Emergency Dispensing Site (EDS) at Holyoke War Memorial Building 310 Appleton Street Holyoke, MA 01040

### February 10, 2017, 8:00AM

### Media coverage has increased as the event unfolds and more people are rushing to Holyoke Medical Center.  There has been a request to activate Holyoke Emergency Dispensing Site located at 310 Appleton Street and have all EDS staff to arrive by 9:00AM and to receive SNS supplies of Doxycycline from the state.

Report of the summary of Victims

As of February, 10, 8:30AM

Hospitalized 	7

Total discharged 	208

Total deceased 	1

Key Activities

- EDS Activation

- Volunteer Management

- Medical Counter Measures

EDS Command

| Role | Name | City/Town Department |
| --- | --- | --- |
| Operations Section Chief/EDS Director | Brian Fitzgerald/Jeanne Galloway | Holyoke Board of Health/PH |
| Incident Commander | Chief John Pond | Fire Department |
| Clerical Unit Supervisor/ Planning Section Chief | Sean Gonsalves/ Lynn Diniz | Holyoke Board of Health |
| Logistics Section Chief | Steve Riffenburg/Erica Johnson | Board of Health/CERT |
| Security Officer/Police | Steve Riffenburg/Holyoke Aux Police Officers | War Memorial |
| Medical Officer/Clinical Unit Supervisor | Deborah Schaier RN/ Carrie Matusko RN | Board of Health |
| Volunteer Management | Lois Luniewicz/Della Marie D’Antonio/Loren Divine/Elsie Diaz/Beverly Hirshhorn | Hampden County |
| MDPH | Michael Nelson/Stephanie Bozigian-Merrick | MDPH/PH |
| Volunteer Actor Roles/EDS Staffing | Johanna Kolodziej/Mary Cornell/Patricia Twinning/Karen Aiken/Audrey Kilcoyne | Holyoke Community College |
| Drive-through/street signage | Dave Beaudoin | Holyoke DPW |
| Drill Coordinator | Liisa Jackson | Facilitator |

# Stage 2: Response Underway

### February 10, 2017, 9:00 AM

Response agencies are in motion and have mobilized their personnel and assets to the War Memorial Building. Hampden County Health Coalition, EDS Staff, Volunteer Coordinators and the City of Holyoke officials are on site to receive further instructions on how to proceed with the response operation. CERT and staff set up EDS stations.

### February 10, 2017, 9:30 AM

The Emergency Dispensing Site at Holyoke War Memorial Building 310 Appleton Street Holyoke, MA Volunteer Reception is open and ready to receive volunteers and give out assignments.  City of Holyoke officials have just received 300 doses of Doxycycline along with the documentation and medication information sheets and checks

### February 10, 2017, 9:45AM

EDS Command Staff check that all stations are operational

### February 10, 2017, 10:00AM

Volunteers continue to arrive and are directed to the volunteer reception center to receive assignments, volunteers should be bringing their badges or government IDs and MRC shirts, of they don’t have shirts will provide them for them (MRC unit leaders please bring extra MRC shirts). HCC/Staff students will be bringing their College ID’s and will be wearing their nursing uniforms.

Summary if Casualties

February 10, 2017, 10:00 AM

Hospitalized 	10

Total discharged 	284

Total deceased 	3

Key Objectives

- Volunteer Management: Receiving volunteers-assignment of rolls-just in time training using Job Action Sheets

- Medical Counter Measures: Public Health Advisory: Doxycycline for Anthrax Exposure

- The currently recommended dosage regimen of doxycycline for severe disease is 100 mg every 12 hours for adults and 1mg per pound (2.2mg per kilogram) every 12 hours for children less than 100 pounds. These dosage regimens are appropriate for use in patients who have been exposed to anthrax (Bacillus anthracis) regardless of the route of exposure.

Briefing

### February 10, 2017, 10:30AM

- Drill Instructions

- EDS Flow Chart

- EDS Station Supervisor Introductions

- Mobilization of Stations

- Just in time training at each dispensing site station

Stage 3: EDS Open

February 10, 2017, 11:00 AM

Holyoke EDS is open to run through scenarios: Holyoke Community College Students will start playing out scenarios: staff and student will be wearing their Holyoke Community College ID’s

February 10, 2017, 11:15 AM

Inject: the press arrives and demands entry and asking people in line if they are feeling.

February 10, 2017, 11:30AM

Inject: Patient passes out and needs to be transported to the hospital

February 10, 2017, 11:45 AM

Inject: supplies are running low and a request for more is put in

February 10, 2017, 11:45 PM

Inject: A high powered state official comes to visit EDS

February 10, 2017, 12:00 PM

EDS Demobilization

Demobilize station

Return Equipment to staging area

Each Station Supervisor identify 3 successes and 3 gaps in each the 4 stages of the Drill:

Mobilization

Station Just in Time Training using job action sheets

Ongoing Operations

Demobilization

Everyone grabs lunch and comes to Briefing area

Hot-wash February 10, 2017, 12:15 PM

### Hot-wash discussion:

### Each Station Supervisor will report back on 3 challenges and 3 successes in each the 4 stages of the Drill:

- Mobilization

- Station Just in Time Training

- EDS operations

- Demobilization

February 10, 2017, 1:00 PM

CERT and EDS staff demobilizes

# Appendix A: Agent Summary-Bacillus Anthracis

- SUMMARY OF AGENT

Anthrax is a highly lethal infection caused by infection with the Gram-positive bacterium, Bacillus anthracis.  In naturally acquired cases, organisms usually gain entrance through skin wounds (causing a localized infection), but may be inhaled or ingested.  Intentional release by belligerents or terrorist groups would presumably involve the aerosol route, because the spore form of the bacillus is quite stable and possesses characteristics ideal for the generation of aerosols.

- SIGNS AND SYMPTOMS

The incubation period for inhalational anthrax is 1 to 6 days.  Fever, malaise, fatigue, coughing, and mild chest discomfort are rapidly followed by severe respiratory distress with dyspnea, diaphoresis, stridor, and cyanosis.  Shock and death occur within 24 to 36 hours of the onset of severe symptoms.  In cases of cutaneous anthrax, a papule develops, then vesicates, finally developing into a black eschar surrounded by moderate to severe edema.  The lesions are usually painless.  Without treatment, the disease may progress to septicemia and death, with a case fatality rate of 20 percent.  With treatment, fatalities are rare.

- DIAGNOSIS

Physical findings are typically nonspecific in inhalational cases, with initial complaints of malaise, fever, headache, and possibly substernal chest pain.  A widened mediastinum is sometimes seen on x-ray late in the course of illness, and correlates with a pathologic finding of hemorrhagic mediastinitis, the “classic” presentation of inhalational anthrax.  The bacterium may be detected by Gram’s-stain of blood and blood culture late in the course of illness.

- TREATMENT

Although usually ineffective in inhalational cases once symptoms are present, antibiotic treatment with high-dose penicillin, ciprofloxacin, or doxycycline should nonetheless be administered.  Although typically sensitive T2:  HPBXLA to penicillin, resistant isolates are readily produced in the laboratory.  For this reason, in the case of an intentional release, and in the absence of antibiotic sensitivity data, treatment should be initiated with intravenous (IV) ciprofloxacin (400 mg q 8 to 12 hours) or IV doxycycline (200 mg initially, followed by 100 mg q 12 hours).  Supportive therapy may be necessary.

- PROPHYLAXIS

A licensed vaccine is available for those at risk of exposure.  Vaccination is undertaken at 0, 2, and 4 weeks (initial series), followed by booster doses at 6, 12, and 18 months, and then yearly.  Oral ciprofloxacin (500 mg po bid) or doxycycline (100 mg po bid) is useful in cases of known or imminent exposure.  Following confirmed exposure, all unimmunized individuals should receive three 0.5 ml SQ doses of vaccine during 30 days, while those vaccinated with < 3 doses prior to exposure should receive an immediate 0.5 ml booster.  Anyone vaccinated with the initial 3-dose series in the previous 6 months does not require boosters.  All exposed personnel should continue antibiotic therapy for 4 weeks.  If vaccine is unavailable, antibiotics may be continued beyond 4 weeks and should be withdrawn only under medical supervision.

- DECONTAMINATION AND ISOLATION

Drainage and secretion precautions should be practiced.  Anthrax is not known to be transmitted via the aerosol route from person to person.  Following invasive procedures or autopsy, instruments and surfaces should be thoroughly disinfected with a sporicidal agent (high-level disinfectants such as iodine or 0.5 percent sodium hypochlorite).

- OUTBREAK CONTROL

Although anthrax spores may survive in the environment for many years, secondary aerosolization of such spores (such as by pedestrian movement or vehicular traffic) generally presents no problem for humans.  The carcasses of animals dying in such an environment should be burned, and animals subsequently introduced into such an environment should be vaccinated.  Meat, hides, and carcasses of animals in affected areas should not be consumed or handled by untrained and/or unvaccinated personnel.

# Appendix B: Acronym & Abbreviation List

This is a sample list of Acronyms and Abbreviation that you may need.  Feel free to delete the ones not relevant to this exercise.

A	AAR			After-Action Report

ACS			Alternate Care Site

ALS			Advanced Life Support

B	BLS			Basic Life Support

BW			Biological Weapons

C	C3			Command, Control, and Communication

CBRNE		Chemical/Biological/Radiological/Nuclear High-Yield Explosive

CDC			Centers for Disease Control and Prevention

CISD			Critical Incident Stress Debriefing

CISM			Critical Incident Stress Management

CONPLAN		Concept of Operations Plan

COOP			Continuity of Operations

D	DMAT			Disaster Medical Assistance Team

DMORT		Disaster Mortuary Operational Response Team

DPS			Department of Public Safety

DPW			Department of Public Works

E	EDS			Emergency Dispensing Site

EEG			Exercise Evaluation Guide

EMA			Emergency Management Agency

EMS			Emergency Medical Services

EMT			Emergency Medical Technician

EOC			Emergency Operations Center

EOP			Emergency Operations Plan

EOPSS		Executive Office of Public Safety and Security

F	FE			Functional Exercise

FEMA			Federal Emergency Management Agency

FSE			Full-Scale Exercise

H	HHAN			Health and Homeland Alert Network

HazMat		Hazardous Materials

HHS			Department of Health and Human Services

HSEEP 		Homeland Security Exercise and Evaluation Program

I	I & Q			Isolation and Quarantine

ICS			Incident Command System

ICU			Intensive Care Unit

IED			Improvised Explosive Device

IND			Investigational New Drug

IP			Improvement Plan

J	JIC			Joint Information Center

JOC			Joint Operations Center

JPIC			Joint Public Information Center

M	MACC			Multi-Agency Coordination Center

MCI			Mass Casualty Incident

MDPH			Massachusetts Department of Public Health

MEMA		Massachusetts Emergency Management Agency

MMRS		Metropolitan Medical Response System

MOU			Memorandum of Understanding

N	NDMS			National Disaster Medical System

NIH			National Institutes of Health

NIMS			National Incident Management System

NIOSH		National Institute of Occupational Safety and Health

O	ODP			Office for Domestic Preparedness

OEM			Office of Emergency Management

OSHA			Occupational Safety and Health Administration

P	PCR			Polymerase Chain Reaction

PIO			Public Information Officer

POC			Point of Contact

PPE			Personal Protective Equipment

PTSD			Post-Traumatic Stress Disorder

R	ROC			Regional Operations Center

S	SITMAN		Situation Manual

SITREP		Situation Report

SNS			Strategic National Stockpile

SOP			Standard Operating Procedure

SWAT			Special Weapons and Tactics

T	TARU			Technical Advisory Response Unit

TCL			Target Capability List

TEP			(Multiyear) Training and Exercise Plan

TTX			Tabletop Exercise

U	UCS			Unified Command System

US&R			Urban Search and Rescue

USDHS		U.S. Department of Homeland Security

USPHS		U.S. Public Health Service

UTL 			Universal Task List

W	WMD			Weapon(s) of Mass Destruction

# Appendix C: Key Terminology

This section contains definitions of key terms used throughout this document, as well as other exercise related material.  Please add or delete terms and definitions as you see fit.

After Action Report and Improvement Plan (AAR/IP): The main product of the Evaluation and Improvement Planning process is the AAR/IP. The AAR/IP has two components: an AAR, which captures observations of an exercise and makes recommendations for post-exercise improvements; and an IP, which identifies specific corrective actions, assigns them to responsible parties, and establishes targets for their completion. The lead evaluator and the exercise planning team draft the AAR and submit it to conference participants prior to the After Action Conference. The draft AAR is completed first and distributed to conference participants for review no more than 30 days after exercise conduct. The final AAR/IP is an outcome of the After Action Conference and should be disseminated to participants no more than 60 days after exercise conduct. (Source: HSEEP Glossary)

Capability: A capability may be delivered with any combination of properly planned, organized, equipped, trained, and exercised personnel who achieve the intended outcome. Descriptions of these combinations can be found in the TCL for each capability. This combination of resources provides the means to accomplish one or more tasks under specific conditions and meet specific performance standards. (Source: HSEEP Glossary)

Critical Task: Critical tasks are defined as those prevention, protection, response, and recovery tasks that require coordination among an appropriate combination of Federal, State, local, tribal, private sector, and non-governmental entities during a major incident in order to minimize the impact on lives, property, and the economy. Participants must perform critical tasks in order to prevent occurrence of a major incident; respond and reduce loss of life or serious injuries; or mitigate significant property damage, all of which are essential to the success of a homeland security mission. (Source: HSEEP Glossary)

Discussion Based Exercise: Discussion-based exercises are normally used as a starting point in the building-block approach to the cycle, mix, and range of exercises. Discussion-based exercises include seminars, workshops, TTXs, and games. These types of exercises typically highlight existing plans, policies, mutual aid agreements, and procedures, and are exceptional tools to familiarize agencies and personnel with current or expected jurisdictional capabilities. Discussion-based exercises typically focus on strategic, policy-oriented issues, whereas operations-based exercises tend to focus more on tactical, response-related issues. Facilitators and/or presenters usually lead the discussion and keep participants on track to meet exercise objectives. (Source: HSEEP Glossary)

Drill: A drill, a type of operations-based exercise, is a coordinated, supervised activity usually employed to test a single specific operation or function in a single agency. Drills are commonly used to provide training on new equipment, develop or test new policies or procedures, or practice and maintain current skills. (Source: HSEEP Glossary)

Emergency Dispensing Site (EDS): Individual venues strategically placed across the community and used as temporary clinics for dispensing medical counter-measures in the event of a public health emergency.

Exercise Evaluation Guide (EEG): EEGs are HSEEP documents that support the exercise evaluation process by providing evaluators with consistent standards for observation, analysis, and AAR development. Each EEG is linked to a target capability and provides standard activities, performance measures, and tasks to be evaluated based on the exercise objectives. Additionally, an EEG contains a Capability Narrative section, in which evaluators provide a general chronological narrative of exercise events associated with the capability; and an Evaluator Observations section in which evaluators provide specific strengths and areas of improvement linked to the capability. The consistent guidelines provided in EEGs facilitate creation of AAR/IPs resulting in an actionable IPs that target specific personnel, planning, organization, equipment, and training needs within capabilities. (Source: HSEEP Glossary)

Full Scale Exercise (FSE): An FSE is a multi-agency, multi-jurisdictional activity involving actual deployment of resources in a coordinated response as if a real incident had occurred. An FSE tests many components of one or more capabilities within emergency response and recovery, and is typically used to assess plans and procedures under crisis conditions, and assess coordinated response under crisis conditions. Characteristics of a FSE include mobilized units, personnel, and equipment; stressful, a realistic environment, and scripted exercise scenarios. (Source: HSEEP Glossary)

Functional Exercise (FE): An FE is a single or multi-agency activity designed to evaluate capabilities and multiple functions using a simulated response. An FE is typically used to: evaluate the management of Emergency Operations Centers (EOCs), command posts, and headquarters; and assess the adequacy of response plans and resources. Characteristics of an FE include simulated deployment of resources and personnel, rapid problem solving, and a highly stressful environment. (Source: HSEEP Glossary)

Homeland Security Exercise and Evaluation Program (HSEEP): HSEEP is a capabilities- and performance-based exercise program that provides standardized policy, doctrine, and terminology for the design, development, conduct, and evaluation of homeland security exercises. HSEEP also provides tools and resources to facilitate the management of self-sustaining homeland security exercise programs. (Source: HSEEP Glossary)

Improvement Plan (IP): For each task, the IP lists the corrective actions that will be taken, the responsible party or agency, and the expected completion date. The IP is included at the end of the AAR. (Source: HSEEP Glossary)

Incident Command System (ICS): A standardized on-scene emergency management construct specifically designed to provide for the adoption of an integrated organizational structure that reflects the complexity and demands of single or multiple incidents, without being hindered by jurisdictional boundaries.  ICS is the combination of facilities, equipment, personnel, procedures, and communication operating with a common organizational structure, designed to aid in the management of resources during incidents.  ICS is used for all kinds of emergencies and is applicable to small as well as large complex incidents.  ICS is used by various jurisdictions and functional agencies, both public and private, or organized field-level incident management operations. (Source: FEMA, NIMS Compliance Metrics)

Multi-year Training and Exercise Plan (MTEP or TEP): The Multi-Year Training and Exercise Plan is the foundational document guiding a successful exercise program. The multi-year plan provides a mechanism for long-term coordination of training and exercise activities toward a jurisdiction’s preparedness goals. This plan describes the program’s training and exercise priorities and associated capabilities, and aids in employing the building-block approach for training and exercise activities. As training and exercises are completed, the document can be annually updated, modified, and revised to reflect changes to the priorities and new capabilities that need to be assessed. The Multi-year Training and Exercise Plan and schedule are produced through the work completed at the Training and Exercise Plan Workshop (T&EPW). The T&EPW focuses on discussion of capabilities-based planning, overview of the National Priorities, review of the State or jurisdiction priorities, and analysis of previous training and exercises. After this information is synthesized, participants develop the plan and schedule for their State or jurisdiction. (Source: HSEEP Glossary)

National Incident Management System (NIMS): The NIMS standard was designed to enhance the ability of the United States to manage domestic incidents by establishing a single, comprehensive system for incident management. It is a system mandated by HSPD-5 that provides a consistent, nationwide approach for Federal, State, local, and tribal governments, the private sector, and non-governmental organizations to work effectively and efficiently together to prepare for, respond to, and recover from domestic incidents, regardless of cause, size, or complexity. (Source: HSEEP Glossary)

National Priorities: The national priorities were developed after a review of national strategies, directives, Department of Homeland Security (DHS) objectives and priorities, and State homeland security strategies. The priorities fall into two categories: overarching priorities that contribute to development of multiple capabilities, and capability-specific priorities that build selected capabilities from the TCL for which the Nation has the greatest need. Achieving the priorities will help advance national Homeland Security objectives. (Source: USDHS, “A Common Starting Point: The National Priorities”)

Operations Based Exercise: Operations-based exercises are a category of exercises characterized by actual response, mobilization of apparatus and resources, and commitment of personnel, usually held over an extended period of time. Operations-based exercises can be used to validate plans, policies, agreements, and procedures. They include drills, FEs, and FSEs. They can clarify roles and responsibilities, identify gaps in resources needed to implement plans and procedures, and improve individual and team performance. (Note: These exercises often follow after, and validate, the lessons learned from discussion-based exercises.) (Source: HSEEP Glossary)

Program Priorities: Priorities will vary by town, city, region/coalition or jurisdiction.  They are derived from previous exercise After Action Reports, Improvement Plans, Federal and State reviews and the overall Homeland Security Strategy for the state/commonwealth.  Program Priorities should reflect the planning and resource focus of the organization(s) that develop the Multi-year Training and Exercise Plan (TEP).  Trainings and exercises outlined in the TEP should support these specific priorities.

Seminars: Seminars orient participants to authorities, strategies, plans, policies, procedures, protocols, resources, concepts, and/or ideas. Seminars provide a good starting point for jurisdictions that are developing or making major changes to their plans and procedures. (Source: HSEEP Glossary)

Situation Manual (SITMAN): The SitMan is a handbook provided to all participants in discussion-based exercises, particularly TTXs. The SitMan provides background information on the exercise scope, schedule, and objectives. It also presents the scenario narrative that will drive participant discussions during the exercise. (Note: The SitMan should mirror the exercise briefing, support the scenario narrative, and allow participants to read along while watching events unfold).

Standard Operation Procedures (SOP): A complete reference document that details the procedures for performing a single function or a number of interdependent functions. (Source: FEMA, NIMS Compliance Metrics)

Tabletop Exercise (TTX): TTXs are intended to stimulate discussion of various issues regarding a hypothetical situation. They can be used to assess plans, policies, and procedures or to assess types of systems needed to guide the prevention of, response to, or recovery from a defined incident. During a TTX, senior staff, elected or appointed officials, or other key personnel meet in an informal setting to discuss simulated situations. TTXs are typically aimed at facilitating understanding of concepts, identifying strengths and shortfalls, and/or achieving a change in attitude. Participants are encouraged to discuss issues in depth and develop decisions through slow-paced problem-solving rather than the rapid, spontaneous decision-making that occurs under actual or simulated emergency conditions. TTXs can be breakout (i.e., groups split into functional areas) or plenary (i.e., one large group). (Source: HSEEP Glossary)

Target Capabilities List (TCL): The TCL is a list of capabilities that provides guidance on the specific capabilities that Federal, State, tribal, and local entities are expected to develop and maintain to prevent, protect against, respond to, and recover from incidents of national significance, including terrorism or natural disasters, in order to maintain the level of preparedness set forth in the National Preparedness Goal. (Source: HSEEP Glossary)

Universal Task List (UTL): The UTL is a comprehensive menu of tasks derived from all tasks that may be performed in major incidents as illustrated by the National Planning Scenarios. Entities at all levels of government should use the UTL as a reference to help them develop proficiency through training and exercises to perform their assigned missions and tasks during major incidents. (Source: HSEEP Glossary)

Workshop: The workshop, a type of discussion-based exercise, represents the second tier of exercises in the building-block approach. Although similar to seminars, workshops differ in two important aspects: increased participant interaction, and a focus on achieving or building a product (e.g., plans, policies). A workshop is typically used to: test new ideas, processes, or procedures; train groups in coordinated activities; and obtain consensus. Workshops often use breakout sessions to explore parts of an issue with smaller groups. (Source: HSEEP Glossary)