Proposed Timeline for Development of Business Continuity Plan

2004-2007

| Date | Action | Comments |
| --- | --- | --- |
| December 2004 | Development of IS Risk Assessment | Annual review with recommendations |
| June 2005 | Update IS Business Continuity & Disaster Recovery Plan | Complete |
| July 2005 | Finalize IS Risk Assessment | Complete |
| September-November 2005 | Attend presentations on risk assessment, risk mitigation, and business continuity | Complete |
| December 2005 | Introduce campus leadership to business continuity | Planning consultant during annual Quality Conference |
| January 2006 | Form an advisory committee/leadership | Phase I |
| February 2006 | Identify potential campus-wide hazards, current plans and resources | Phase I |
| March 2006 | Create college continuity template; pilot with unit(s) | Phase I |
| April 2006 | Educate campus leadership related to template | Phase I – Annual College Strategic Planning Meeting |
| May – October 2006 | Hazard identification and risk assessment by department | Phase II |
| November 2006 | Results of hazard identification and risk assessment by department | Phase II – Annual Quality Conference |
| December 2006 – March 2007 | Develop mitigation plans by department | Phase III – Feed into annual program reviews/ budget concerns |
| April 2007 | Finalize departmental plans; campus leadership reacts to plan | Phase III – Annual College Strategic Planning Meeting; relate to budget requests as appropriate |
| May – June 2007 | Adoption and Implementation of Plan | Phase IV - Blessed by campus, president and BOT |