NCRTAC Executive Council Meeting

January 15, 2020
Teleconference

- Call to Order

  - Dr. Roberts, Gina Brandl, Del Horn, Penny Radlinger, Jeff Nuernberger, Michael Fraley, Kelly Bechel, Jason Keffeler, Kenneth Marg, Dr. Clark

- Correspondence

  - None

3. Approval of July 25, 2019 minutes

Del Horn 1 / Jason Keffler 2

Minutes approved / No nays

4. Discussion & possible action: 2019-2020 Budget update

5. Discussion & possible action: 2020 Hospital/EMS project grant application

Updated last year’s form (change from 2019 to 2020)

Effective tomorrow to announce at RTAC

Grants due 2/15 and will be awarded 2 weeks after that

No approval needed

6. Discussion & possible action: NCRTAC Trauma Conference 2020 budget

See budget.

Voted to stay within 10% of proposed budget

Jason Keffeler 1 / Dr. Roberts 2

Approved – no nays

7. Discussion & possible action: Regional trauma plan revision

Survey for action items for next trauma plan – 12 responses. Will extract 		action items from that – Michael. Will get to members

No action needed.

8. Discussion & possible action: 2019-2020 NCRTAC work plan update

Confusing – 2 documents

Scope of work – RTAC – 6 items

Work plan – 21 items Michael is working on. Focused on what he does and is submitted to state. 5 are done, 11 semi/quarterly and on schedule with those, 1 action no submission date/data, 2 – attendance and participation at state meeting, 1 regional drill (CWA drill and coalition) and regional trauma plan and submit (end of June). All on track.

9. Other Business for NCRTAC Executive Council consideration

Michael Fraley – none

Chris, Del & Penny can review grants

Have a lot of tourniquets available – talk with out of hospital committee tomorrow at RTAC

10. Need to set future meeting agenda items

DHS 118 – no update.

Caitlyn will be calling into meeting tomorrow.

11. Adjournment