## Slide 1: Call 4 Concern© roll out plan
 | Actions required | Owner of actions | RAG rated progress | Precited date of completion
Resources |  |  |  | 
Patient/ relative information leaflet | 1. Amend digital version of C4C leaflet template 2. Circulate draft leaflet to relevant governance committee for comments 3. Submit leaflet to patient information leaflet panel for approval 2. Contact printing company to obtain quote 3. Discuss with procurement team to raise updated non- catalogue order number 4. Distribute to relevant areas including Critical Care Unit for step-downs. 5. Advice admin staff details for reorder |  |  | 
Banner/Stand | 1. Curate digital banner draft 2. Contact company & obtain quote 3. Raise with procurement for non-catalogue order 4. Order and distribute to relevant public areas |  |  | 
Posters | 1. Amend digital version of C4C poster template 2. Contact company & obtain quote 3. Raise with procurement for non-catalogue order Or Print and laminate using internal equipment 4. Order and distribute to relevant public areas |  |  | 
Mobile Phone with voicemail facilities | 1.Discuss with manager procurement for mobile 2.Contact IT team and complete order 3.When mobile obtained, record voice message 4.Advertise number on leaflets/ banner/ posters etc. |  |  | 

## Slide 2
 | Actions required | Owner of actions | RAG rated progress | Precited date of completion
Education |  |  |  | 
BLS/ILS/deteriorating patient/ staff induction training Call 4 Concern to be covered in training, can be incorporated into escalation targeted training already being delivered | 1. Liaise with team who deliver deteriorating patient training 2.C4C to be added to targeted training presentations |  |  | 
Ward practice improvement facilitators/ Call 4 Concern Champions Utilised our deteriorating patient practice improvement facilitators/ Call 4 Concern Champions to support roll out/ engagement and education of C4C to ward areas. | 1. Recruit volunteers from practice improvement facilitators and trust wide to become Call 4 Concern Champions 2. Meet with Champions to give brief overview of C4C and expectations of this role. Opportunity for staff to brainstorm ideas how this could be best introduced and embedded. 3. Produce bite size education package that C4C can use to deliver short teaching on to colleagues within ward areas. |  |  | 
Doctors teaching It is key they we ensure the message reached all of our colleagues, including our doctors. | 1. C4C awareness training to doctors may be received better coming from a medical lead. Utilise medical lead or medical director to deliver information. 2. Confirm what teaching opportunities there are for all doctors from all divisions, not just medical doctors. Again, could this be done by a medical lead. |  |  | 
AHP teaching opportunities | 1. Confirm opportunities for teaching AHP |  |  | 

## Slide 3
 | Actions required | Owner of actions | RAG rated progress | Precited date of completion
Dissemination/ Spread |  |  |  | 
Trust wide newsletter + deteriorating patient newsletter could feature a section on Call 4 Concern | 1. Confirm who produces trust wide newsletter/ deteriorating patient newsletter 2. Draft entry about C4C into newsletter |  |  | 
Trust internal comms Facebook page | 1. Post information regarding Call 4 Concern initiative |  |  | 
Sharing events use this as a forum to share the initiative and raise awareness | 1. Contact organisers to arrange presenting at next event 2. Utilise teaching PowerPoint template |  |  | 
Call 4 Concern Champions (as detailed in education) |  |  |  | 
Sisters / Matrons forums potentially could this be presented either by CCO team or one of the nursing leads | 1. Confirm dates for next Sisters / Matrons forums 2. Utilise teaching PowerPoint template |  |  | 
Screen savers / trust wide email | 1. Liaise with comms team |  |  | 
Trust/ team external comms | 1.Discuss with comms team options 2.Consider using trust website 3.External trust and team social media i.e facebook/ X (twitter) 4.Local news |  |  | 

## Slide 4
 | Actions required | Owner of actions | RAG rated progress | Precited date of completion
Embed/ Evaluate |  |  |  | 
Ongoing data on the use of peri arrest calls, occurrence of serious incidences related to deteriorating incident and in hospital cardiac arrests Could monitor this data following the roll out of C4C to see if incidences of failure to identify/ recognise/ respond to deteriorating patients reduce. | 1. Ongoing monitoring and reporting |  |  | 
Patient and relative feedback Measure service aim of improving patient/ relative experience. Opportunity to explore what works and what could be better | 1.Liaise with IT service to set up a digital survey 2. Utilise patient and relative feedback survey template for questions 3.Audit and collate results monthly/ 6 monthly 4.Share results with governance committees |  |  | 
Call 4 Concern Log | 1.Set up C4C log (use exel template as required) 2.CCOT to complete every time they receive C4C referral 3.Audit and collate results monthly 4.Share results with governance committees |  |  | 
PALS | 1.Liaise with PALS 2.Discuss ways to monitor if complaints reduce as a result of C4C |  |  | 
Consistent exposure and education | As detailed in education |  |  |