## Slide 1
Solaris 10 to 11
Migration and Preparation

## Slide 2: Solaris 10 to Solaris 11 Migration Project Goals
Migrate 57 NC Community Colleges’ production and DR servers from Solaris 10 to 11 before the end of January 2018.
Maximize manageability and portability of the Solaris 11 and Colleague environments through standardization of server configurations.
Perform server management in compliance with State/IIPS Security Standards.

## Slide 3: Solaris 10 to Solaris 11 Migration Assumptions
Colleges will have two M-series or T-series servers (Typically production and DR) or utilize a hosted or other vendor-provided server (at least for the migration) -* This may require Ellucian approval of the hosting site. Ellucian does not officially support Oracle servers other than the M-series
The DR server has adequate disk space to store the production, test, and development environments and associated LPR(s) (Minimum needed space=Solaris 11 OS (300Gb) + 2x the size of Colleague environments)
The DR server will have adequate memory and processing capability to operate critical production needs over a 2 to 4 day migration window. (This may be mitigated by utilizing vendor-provided equipment)
The system administrator possesses the knowledge to perform the file system conversion from UFS to ZFS. (This may be mitigated by the college hiring a knowledgeable vendor to provide the migration support to the college)
The system administrator possesses the knowledge to perform the migration to Solaris 11 (This may be mitigated by the college hiring a knowledgeable vendor to provide the migration support)
The system administrator possesses the knowledge to support Solaris 11, ZFS file systems and snapshots, post-conversion. (A gap can be mitigated, to some extent, via training)

## Slide 4: Solaris 10-11 Migration Phases
The migration is divided in to 2 phases
  1. Pre-Migration
  2. Migration
  This presentation will focus on pre-migration tasks.

## Slide 5
Task # | Pre-Migration Tasks | All/Dev/ Production Servers | Complete By
1 | Run presysinfo script to gather system information and manually ftp following instructions provided in the script | All servers | 02/10/17
2 | Ensure you have mirrored root disk drives (or a 2nd available disk drive of equivalent size or greater than the root drive) | All servers | 03/30/17
3 | Implement Password Job Aid (available from NCLOR) | All servers | 02/10/17
4 | Use BASH shell for OS System Administrator use (will be default in Solaris 11) and continue to use ksh for Colleague | All servers | 02/10/17
5 | Install and configure sudo and become familiar using it to perform system tasks rather than su'ing to root | All servers | 02/28/17
Premigration Steps to perform now

## Slide 6
Task # | Pre-Migration Tasks | All/Dev/ Production Servers | Complete By
7 | Provide DNS names for each environment application | Network/ All servers | TBD
8 | Update the pre-authenticated servers in SA-Valet | All Production servers | TBD
9 | Convert Colleague external application servers to use DNS names (UI, E-Commerce, E-Procurement, E-Transcript, FA-Link, inventory scanners, etc.) | Network/ All servers | TBD
10 | Convert root disk to mirrored ZFS pool with root and var as separate data sets | All servers | 07/31/17
11 | Modify your patch process to use alternative boot environments | All servers | 07/31/17
12 | Backups will likely need to be adjusted to pause db, snapshot, resume db, backup db | All servers | 07/31/17
13 | Clone Colleague environments with ZFS using ZFS tools | All servers | 07/31/17
14 | Develop competency managing snapshots (training and experience) | All servers | 07/31/17
Premigration Steps

## Slide 7
Task # | Pre-Migration Tasks | All/Dev/ Production Servers | Complete By
13 | Bind each environment to its own IP Address using the same port numbers for the listeners | All servers | TBD
14 | Close down unneeded ports once DNS setup is complete and tested | Network | TBD
15 | Java 8 upgrade | All servers | TBD
16 | Unidata 8.1.2+ upgrade | All servers | TBD
17 | UI 5 implementation | All servers | TBD
Premigration Steps

## Slide 8: Next steps
Distribute the Premigration task list to the colleges
Colleges download/run the presysinfo script and upload results
Thursday SA maintenance calls will cover specific topics to support the pre-migration tasks
Provide Solaris 11 training information and cost
Provide guidance on the DNS layout

## Slide 9: Discussion and Questions