## Sheet1
BELMONT CONDOMINIUM TRUST REPLACEMENT COSTS 2022 (15 Year with 5% Contingency Included in Estimated Costs) Updated Updated Auguust 20, 2022
|  | EST. REPLACE. | EST. LIFE IN | YEARS TO | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | Future | Total | (Over) Under
| ITEM DESCRIPTION | COST (20 YRS) | YEARS | REPLACE | RESERVE | RESERVE | RESERVE | RESERVE | RESERVE | RESERVE | RESERVE | RESERVE | RESERVE | RESERVE | RESERVE | RESERVE | RESERVE | RESERVE | RESERVE | RESERVE | RESERVE | Budget
C | Roof Building 1/2 (2017) | 500000 | 25 | 17 | [15 empty] | 500000 | 500000 | 0
C | Roof Building 3/4 (2006+22) | 585000 | 25 | 8 | 2030: 385000 | 200000 | 585000 | 0
C | Roof Building 5/6 (2003) | 650000 | 25 | 5 | 2027: 650000 | 0 | 650000 | 0
C | Metal Roof Entrance Building 1 | 15000 | 25 | 15 | [15 empty] | 15000 | 15000 | 0
C | Metal Roof Entrance Building 2 | 15000 | 25 | 15 | [15 empty] | 15000 | 15000 | 0
C | Metal Roof Entrance Building 3 | 15000 | 25 | 3 | 2024: 15000 | 0 | 15000 | 0
C | Metal Roof Entrance Building 4 | 15000 | 25 | 3 | 2024: 15000 | 0 | 15000 | 0
C | Metal Roof Entrance Building 5 | 15000 | 25 | 2 | 2023: 15000 | 0 | 15000 | 0
C | Metal Roof Entrance Building 6 | 15000 | 25 | 2 | 2023: 15000 | 0 | 15000 | 0
C | Roof - Townhouse 1-8 (2003) | 201250 | 30 | 10 | 2032: 201250 | 0 | 201250 | 0
C | Roof - Townhouse 9-24 (2006) | 391000 | 30 | 12 | 2034: 391000 | 0 | 391000 | 0
C | Roof - Townhouse 25-32 (2007) | 218500 | 30 | 13 | 2035: 218500 | 0 | 218500 | 0
C | Roof - Restaurant & Adj. Cabanas (2007) | 149500 | 30 | 13 | 2035: 149500 | 0 | 149500 | 0
C | Roof - Pool Area & Cabanas (2010) | 138000 | 30 | 16 | [15 empty] | 138000 | 138000 | 0
C | Roof - Belmont Entrance (2010) | 30187 | 30 | 16 | [15 empty] | 30187 | 30187 | 0
C | Trim-Pool Area & Cabanas (2010) | 51000 | 30 | 16 | [15 empty] | 51000 | 51000 | 0
C | Pool Rehabilitation | 69000 | 10 | 7 | 2029: 69000 | 0 | 69000 | 0
MR | Build. Envelope Cond. Survey | 46000 | 1 | 0 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 8500 | 46000 | 0
C | Wall Shingling/Trim T/H 1-16 (2001) | 626175 | 25 | 3 | 2025: 626175 | 0 | 626175 | 0
C | Wall Shingling/Trim T/H 17-24 (2002) | 310500 | 25 | 5 | 2027: 310500 | 0 | 310500 | 0
C | Wall Shingling/Trim T/H 25-32 (2007) | 313863 | 25 | 10 | 2031: 313863 | 0 | 313863 | 0
C | Mid-Rise Waterproof Sealer (2016) | 230000 | 10 | 14 | 2035: 230000 | 0 | 230000 | 0
MR | Midrise Building Repair | 300000 | 5 | 1 | 2022: 150000; 2025: 150000 | 0 | 300000 | 0
C | Walks Townhouse 1-32 (2002) | 87342 | 25 | 5 | 2027: 87342 | 0 | 87342 | 0
MR | Carpet Mid-Rise 1/2 (2015) | 86250 | 10 | 6 | 2028: 86250 | 0 | 86250 | 0
MR | Carpet Mid-Rise 3/4 (2017) | 86250 | 10 | 4 | 2028: 86250 | 0 | 86250 | 0
MR | Carpet Mid-Rise 5/6 (2016) | 86250 | 10 | 4 | 2028: 86250 | 0 | 86250 | 0
MR | Lobby/Upper Flr Tile-Bldg. 1 | 6900 | 25 | 5 | 2027: 6900 | 0 | 6900 | 0
MR | Lobby/Upper Flr Tile-Bldg. 2 | 9717 | 25 | 5 | 2027: 9717 | 0 | 9717 | 0
MR | Lobby/Upper Flr Tile-Bldg. 3/4 | 16042 | 25 | 5 | 2027: 16042 | 0 | 16042 | 0
MR | Lobby/Upper Flr Tile-Bldg. 5/6 | 16042 | 25 | 5 | 2027: 16042 | 0 | 16042 | 0
MR | Garage Lobby Flr Tile-Bldg. 1/2 | 8912 | 25 | 5 | 2027: 8912 | 0 | 8912 | 0
MR | Garage Lobby Flr Tile-Bldg. 3/4 | 6612 | 25 | 5 | 2027: 6612 | 0 | 6612 | 0
MR | Garage Lobby Flr Tile-Bldg. 5/6 | 6612 | 25 | 6 | 2027: 6612 | 0 | 6612 | 0
MR | Mid-Rise Balcony Walls Bldg.1-6 | 1150000 | 25 | 14 | 2036: 1150000 | 0 | 1150000 | 0
MR | Intercom Buildings 1-6 & Pedastals | 30000 | 25 | 2 | 2023: 30000 | 0 | 30000 | 0
MR | Mid-Rise Buidlings Fascia Rehab. | 15000 | 5 | 0 | 2022: 5000; 2028: 5000; 2032: 5000 | 0 | 15000 | 0
MR | Mid-Rise Common Area Windows | 51750 | 25 | 11 | 2033: 51750 | 0 | 51750 | 0
C | Poolside Beach Walkway & Circles | 34500 | 25 | 12 | 2034: 34500 | 0 | 34500 | 0
C | Main Ocean Walk Between 1,2 & 3,4 (2017) | 63250 | 22 | 13 | 2036: 63250 | 0 | 63250 | 0
C | Restaurant Table, Chairs | 57500 | 10 | 4 | 2027: 28750; 2034: 28750 | 0 | 57500 | 0
C | Restaurant Deck Funiture Replace. | 23000 | 10 | 6 | 2029: 23000 | 0 | 23000 | 0
C | Pool Apt. - Trim/Window Replace. | 8625 | 20 | 13 | 2036: 8625 | 0 | 8625 | 0
C | Gated Entry System | 30000 | 20 | 0 | 2022: 30000 | 0 | 30000 | 0
MR | Mid-Rise Corridor Ceilings Bldg. 1 | 28750 | 20 | 5 | 2027: 7187.5; 2028: 7187.5; 2029: 7187.5; 2030: 7187.5 | 0 | 28750 | 0
MR | Mid-Rise Corridor Ceilings Bldg. 2 | 28750 | 20 | 6 | 2028: 7187.5; 2029: 7187.5; 2030: 7187.5; 2031: 7187.5 | 0 | 28750 | 0
MR | Mid-Rise Corridor Ceilings Bldg. 3 | 28750 | 20 | 20 | [15 empty] | 28750 | 28750 | 0
MR | Mid-Rise Corridor Ceilings Bldg. 4 | 28750 | 20 | 0 | 2022: 7187.5; 2024: 7187.5; 2026: 7187.5; 2027: 7187.5 | 0 | 28750 | 0
MR | Mid-Rise Corridor Ceilings Bldg. 5 | 28750 | 20 | 1 | 2023: 7187.5; 2024: 7187.5; 2025: 7187.5; 2026: 7187.5 | 0 | 28750 | 0
MR | Mid-Rise Corridor Ceilings Bldg. 6 | 28750 | 20 | 15 | [15 empty] | 28750 | 28750 | 0
MR | Mid-Rise Cor. Wall & Door Paint. (2017) | 57500 | 16 | 4 | [15 empty] | 57500 | 57500 | 0
MR | Mid-Rise Hallway Upgrades (2014-2017) | 75000 | 20 | 17 | [15 empty] | 75000 | 75000 | 0
MR | Mid-Rise Garage Wall Painting | 20000 | 10 | 6 | 2028: 20000 | 0 | 20000 | 0
MR | Mid-Rise Garage Ceilings | 57500 | 15 | 9 | 2031: 28750; 2032: 28750 | 0 | 57500 | 0
MR | Luggage & Bellmans Carts | 20000 | 15 | 8 | 2030: 20000 | 0 | 20000 | 0
C | New Decking - Pool Interior (2013) | 345000 | 25 | 14 | 2036: 345000 | 0 | 345000 | 0
C | New Decking - Pool Exterior (2014) | 414000 | 25 | 16 | [15 empty] | 414000 | 414000 | 0
C | New Decking - Club House (2015) | 460000 | 25 | 17 | [15 empty] | 460000 | 460000 | 0
C | Restaurant Renovation | 86250 | 20 | 10 | 2032: 86250 | 0 | 86250 | 0
C | Tennis Court Renovation | 126500 | 14 | 15 | 2036: 126500 | 0 | 126500 | 0
C | Retaining Wall - Belmont Road | 15000 | 25 | 7 | 2029: 15000 | 0 | 15000 | 0
C | Retaining Wall - Tennis Courts (2017) | 34500 | 25 | 20 | [15 empty] | 34500 | 34500 | 0
C | Retaining Wall - Gordon Richie Rd | 28750 | 25 | 15 | [15 empty] | 28750 | 28750 | 0
C | Bathroom Renovations - Pool | 25000 | 10 | 12 | 2032: 25000 | 0 | 25000 | 0
MR | Elevator Controls - Buildings 1-6 | 507150 | 20 | 4 | 2026: 155250; 2035: 351900 | 0 | 507150 | 0
MR | Elevator Cab Interiors | 212750 | 19 | 19 | [15 empty] | 212750 | 212750 | 0
C | Swimming Pool Filter | 24150 | 2 | 0 | 2024: 3154; 2028: 3154; 2032: 3154; 2036: 3154 | 11534 | 24150 | 0
C | Swimming Pool Heater | 17250 | 8 | 3 | 2025: 7500; 2029: 7500 | 2250 | 17250 | 0
C | Clubhouse Awning | 30000 | 8 | 0 | 2022: 20000; 2029: 10000 | 0 | 30000 | 0
C | Landscaping Additions & Improv. | 128800 | 10 | 0 | 2022: 16100; 2024: 16100; 2026: 16100; 2028: 16100; 2030: 16100; 2032: 16100; 2034: 16100; 2036: 16100 | 0 | 128800 | 0
C | Bituminous Pavement - Parking Lot | 400000 | 19 | 20 | [15 empty] | 400000 | 400000 | 0
C | Septic System Repairs | 172500 | 20 | 2 | 2024: 172500 | 0 | 172500 | 0
C | Walkway/Island Light Posts | 45000 | 20 | 1 | 2023: 45000 | 0 | 45000 | 0
C | Property Lighting | 10000 | 20 | 1 | 2023: 10000 | 0 | 10000 | 0
C | Clubhouse Restrooms | 13000 | 20 | 1 | 2023: 13000 | 0 | 13000 | 0
MR | Trash Compactor Replacement | 80000 | 20 | 0 | 2022: 39000 | 41000 | 80000 | 0
| Riverside Drive Boundary Fence | 46000 | 20 | 10 | 2032: 46000 | 0 | 46000 | 0
MR | Fire Sprink. Upgrade Mid-Rise | 40250 | 20 | 4 | 2026: 10000 | 30250 | 40250 | 0
MR | Mid-Rise Lobby Décor | 75000 | 20 | 19 | [15 empty] | 75000 | 75000 | 0
MR | Mid-Rise Entrance Ceilings | 34500 | 20 | 11 | 2033: 34500 | 0 | 34500 | 0
C | Beach Tractor & Utility Cart & Truck | 43745 | 10 | 8 | 2030: 43745 | 0 | 43745 | 0
C | Rehabilitation Pool Apartment | 25000 | 15 | 14 | 2036: 25000 | 0 | 25000 | 0
MR | Paint Entranceways MR | 15000 | 10 | 0 | 2022: 7500; 2032: 7500 | 0 | 15000 | 0
MR | HVAC Roof Mid-Rise Build. 1/2 | 17250 | 20 | 9 | 2031: 17250 | 0 | 17250 | 0
MR | HVAC Roof Mid-Rise Build. 3/4 | 8625 | 20 | 9 | 2031: 8625 | 0 | 8625 | 0
MR | HVAC Roof Mid-Rise Build. 5/6 | 17250 | 20 | 9 | 2031: 17250 | 0 | 17250 | 0
C | Townhouse Exterior Fence & Trellis (2017) | 310500 | 20 | 18 | [15 empty] | 310500 | 310500 | 0
MR | Paint Mid Rise Balcony Railings | 56250 | 15 | 1 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 0 | 56250 | 0
C | Eelectrical Panels | 100000 | 30 | 15 | 2024: 33333; 2026: 33333; 2028: 33333 | 1 | 100000 | 0
C | Security System (Camera's) | 15000 | 20 | 15 | [15 empty] | 15000 | 15000 | 0
C | Restaurant Equipment | 34500 | 20 | 0 | 2022: 8300; 2025: 5000; 2028: 5000; 2031: 5000; 2034: 5000 | 6200 | 34500 | 0
MR | Waterproof Balcony Floors | 69000 | 20 | 0 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 4600 | 0 | 69000 | 0
MR | Replace Mid-Rise Garage Doors (2015) | 21000 | 25 | 17 | [15 empty] | 21000 | 21000 | 0
MR | Mid-Rise Water Valves | 34500 | 20 | 11 | 2032: 34500 | 0 | 34500 | 0
C | Sign Replacement (2017) | 6500 | 10 | 10 | 2032: 6500 | 0 | 6500 | 0
C | Playground | 15500 | 10 | 0 | 2022: 15500 |  | 15500 | 0
C | Pool Side Furniture (2016) | 50312 | 15 | 4 | 2026: 50312 | 0 | 50312 | 0
| OPENING CASH BALANCE |  |  |  | 1063236.33 | 1155443.6845 | 1471196.85 | 1680752.5953 | 1393481.8312 | 1653287.8974 | 1063925.8232 | 1314620.4256 | 1819467.7128 | 2023883.2922 | 2351405.3777 | 2661335.9519 | 3392120.87 | 3784335.5403 | 3754988.122
| RESERVE CONTRIBUTION |  |  |  | 400050 | 460057.5 | 487660.95 | 516920.607 | 547935.8434 | 580811.994 | 615660.7137 | 652600.3565 | 691756.3779 | 733261.7605 | 777257.4662 | 823892.9142 | 873326.489 | 925726.0783 | 981269.643
SPECIAL ASSESSMENT
| RESERVE EXPENDITURES | 11394311 |  |  | 309437.5 | 146037.5 | 280312 | 806712.5 | 290220 | 1172654 | 366562 | 149725 | 490070 | 408775.5 | 470854 | 97100 | 486200 | 960750 | 1748479 | 3210422 | 11394311 | 0
| INTEREST/OPERATING ADJ. (2%) (Adj in Formula is 1.5%) |  |  |  | 1594.8545 | 1733.1655 | 2206.7953 | 2521.1289 | 2090.2227 | 2479.9318 | 1595.8887 | 1971.9306 | 2729.2016 | 3035.8249 | 3527.1081 | 3992.0039 | 5088.1813 | 5676.5033 | 5632.4822
| CUMULATIVE RESERVE BALANCE |  |  |  | 1155443.6845 | 1471196.85 | 1680752.5953 | 1393481.8312 | 1653287.8974 | 1063925.8232 | 1314620.4256 | 1819467.7128 | 2023883.2922 | 2351405.3777 | 2661335.9519 | 3392120.87 | 3784335.5403 | 3754988.122 | 2993411.2472
Footnote - We don't expect any special assessements unless we have an unanticipated major expense, such a a septic system failure or major weather event.
In years 2027 and beyond the reserve contribution may need to be increased to avoid future deficit spending.
In the Estimated Replacement Cost Column we have built in a 5 percent contingency per year based on the year the work was completed and the Estimated Life In Years Column