## Current RFC
Id | Responsible Individual | EI Rating | Title - RFC | State | Classification | Planned Start | Module Affected | Priority
100196 | Strayer Vicki | I | ST - XLE.SOC.ACHIEVEMENT.CODES includes an incorrect code | Open | Standard Change - BF | 2008 - 3 Qtr. | Literacy | 4
100212 | Strayer Vicki | I | ST - Accuplacer - Request to use SS# or Colleague Id | Open | Minor Change | 2008 - 3 Qtr. | Academic Records | 4
100289 | Goff Cinda | I | Determine To-System Office- FTP-enabled applications/Password change schedule | Open | Control Setting | 2008 - 3 Qtr. | Other | 4
100317 | Goff Cinda | I | Delivery of UI Web 3.0 | Open | Sub-system Upgrade | 2008 - 3 Qtr. | Other | 4
100057 | Strayer Vicki | II | Migration of the Fire Certification System | Open | Major Change | 2008 - 3 Qtr. | State/Provincial Reporting | 4
100075 | Strayer Vicki | II | ST - XXIR - Space Utilization Report - room numbers that contain a letter are invalid | Open | Standard Change - BF | 2008 - 3 Qtr. | Other | 4
100110 | MacKenzie Ken | II | The XCBB03C process needs to be corrected for the restart of a refund update | Open | Standard Change - BF | 2008 - 3 Qtr. | Accounts Receivable | 4
100117 | Howard Marcus | II | Track UI SSL Implementation | Open | Training/Documentation | 2008 - 3 Qtr. | UI | 4
100136 | Strayer Vicki | II | XXEN - Select returns 0 records | Open | Standard Change - BF | 2008 - 3 Qtr. | State/Provincial Reporting | 4
100165 | MacKenzie Ken | II | AR/CR GL Distribution on CREN | Open | Major Change | 2008 - 3 Qtr. | Cash Receipts | 4
100178 | Burgess Patricia | II | FA Satisfactory Academic Progress and Multiple Active Acad Programs | Open | Standard Change - BF | 2008 - 3 Qtr. | Financial Aid | 4
100189 | Howard Marcus | II | Sun Java Web Server 7.0 | Open | Sub-system Upgrade | 2008 - 3 Qtr. | Sun Web Server | 4
100224 | Ridl Kathy | II | Addition of CIT programs to the NEIT Module | Open | Minor Change | 2008 - 3 Qtr. | Other | 4
100230 | Strayer Vicki | II | CRPFA report is not running efficiently in R18 | Open | Standard Change - OE | 2008 - 3 Qtr. | State/Provincial Reporting | 4
100278 | Strayer Vicki | II | ST-XXIR-Instructional Space Utilization Report truncating course number to 4 characters | Open | Standard Change - BF | 2008 - 3 Qtr. | State/Provincial Reporting | 4
100279 | Strayer Vicki | II | ST-XXIR-program not appending space to building numbers less than 3 characters | Open | Standard Change - BF | 2008 - 3 Qtr. | State/Provincial Reporting | 4
100288 | Busby Annette | II | UI Web 3.x - System Office Installation / Usage Planning and Implementation | Open | New System/Application | 2008 - 3 Qtr. | Systems | 4
100295 | Pickett Angelica | II | AR/CR Workflow and Programmatic Review | Open | Standard Change - BF | 2008 - 3 Qtr. | Other | 4
100296 | Smith Dennis | II | ST - Workflow Management for CE Registration | Open | Minor Change | 2008 - 3 Qtr. | Registration | 4
100301 | Newsome Rick | II | Completion of Business Objects XI implementation | Open | Major Change | 2008 - 3 Qtr. | Business Objects | 2
100322 | Shillu Joseph | II | Computed Column ARA.BALANCE error- Uninitialized Variable Used! Zero Assumed! | Open | Standard Change - BF | 2008 - 3 Qtr. | Accounts Receivable | 4
100066 | Gilchrist Danny | III | CF - POEM/POIL/POIM missing GL account description | Open | Standard Change - BF | 2008 - 3 Qtr. | Purchasing | 4
100099 | Tai-Rowlands Kathy | III | WOMU, WOLI, and WOMI do not display "Additional Status" field in the header | Open | Standard Change - BF | 2008 - 3 Qtr. | Custom Physical Plant | 4
100267 | Howard Marcus | III | Replace the EDX Phantom script with DASP functionality | Open | Control Setting | 2008 - 3 Qtr. | EP System Components | 4
100102 | Cooper Catherine | I | System Office Supply Inventory Module | Open | New System/Application | 2008 - 4 Qtr. | Other | 4
100151 | Hwang Susan | I | ST - Query to generate Enrollment by major | Open | Standard Change - BF | 2008 - 4 Qtr. | Academic Records | 4
100305 | Strayer Vicki | I | BEVL is Not Page Breaking Properly | Open | Minor Change | 2008 - 4 Qtr. | Degree Audit | 4
100312 | Strayer Vicki | I | CRPFA report needs to report only financial aid students who are awarded aide for the reporting term | Open | Standard Change - BF | 2008 - 4 Qtr. | State/Provincial Reporting | 4
100313 | Strayer Vicki | I | ST - GROS - cancels with 'memory fault' if multiple instructors assigned | Open | Standard Change - BF | 2008 - 4 Qtr. | Academic Records | 4
100044 | Shillu Joseph | II | ST - Changes Requested for Debt Setoff | Open | Major Change | 2008 - 4 Qtr. | State/Provincial Reporting | 4
100062 | MacKenzie Ken | II | CAP - With the release of EC3.7, will the System Office be re-releasing the XS.PRINT.CASH.RCPT.ALLOC subroutine | Open | Minor Change | 2008 - 4 Qtr. | Cash Receipts | 4
100071 | Strayer Vicki | II | APPL.ENROLLED is returning "NOT ENROLLED" for every applicant. | Open | Standard Change - BF | 2008 - 4 Qtr. | Other | 4
100073 | Strayer Vicki | II | ST - ICR/XXUW Modification Request | Open | Standard Change - BF | 2008 - 4 Qtr. | State/Provincial Reporting | 4
100085 | Schmidt Philomena | II | Bonus Leave | Open | Minor Change | 2008 - 4 Qtr. | Payroll | 4
100095 | Leung Laurence | II | E-Procurement Auto PO Flag = Yes & Encumbrances | Open | Standard Change - BF | 2008 - 4 Qtr. | E-Procurement Lite | 4
100108 | Shillu Joseph | II | ARCR - XCAR & RTCA Out of Balance & Sponsor Hook Problem | Open | Standard Change - BF | 2008 - 4 Qtr. | Cash Receipts | 4
100137 | Shillu Joseph | II | Sponsorship setup and processing | Open | Control Setting | 2008 - 4 Qtr. | Accounts Receivable | 4
100157 | MacKenzie Ken | II | ARCR - problem getting balances that I need to report to the state for the NC DOR | Open | Minor Change | 2008 - 4 Qtr. | Accounts Payable | 4
100186 | Strayer Vicki | II | Space Utilization Report (XXIR) - Request to add status of "W" to those counted in "use" column calculation | Open | Minor Change | 2008 - 4 Qtr. | Other | 4
100206 | Strayer Vicki | II | ST - CPCC - WA and Multiple active versions of a course | Open | Standard Change - BF | 2008 - 4 Qtr. | Other | 4
100209 | Strayer Vicki | II | CU ICR - Add the key to the COURSE.SECTIONS | Open | Minor Change | 2008 - 4 Qtr. | State/Provincial Reporting | 4
100232 | Strayer Vicki | II | Has NCCCS licensed Data Orchestrator for use at the colleges | Open | New System/Application | 2008 - 4 Qtr. | Other | 4
100262 | Strayer Vicki | II | ST - XATR - Request that attendance roster print the primary program | Open | Minor Change | 2008 - 4 Qtr. | Academic Records | 4
100098 | Cooper Catherine | III | Purge of WORKORDER record should also purge co-file XFM.WORKORDERS record | Open | Standard Change - BF | 2008 - 4 Qtr. | Custom Physical Plant | 4
100130 | Tai-Rowlands Kathy | III | CF-XMEA - Issue date defaults as current date and the user can not change it-Wayne | Open | Minor Change | 2008 - 4 Qtr. | Key Inventory | 4
100090 | MacKenzie Ken | IV | Update all 2-12 Report documentation | Open | Training/Documentation | 2008 - 4 Qtr. | Cash Receipts | 4
100166 | Leung Laurence | IV | CF-There is no mnemonic to list the requisitions done by department-Caldwell | Open | Minor Change | 2008 - 4 Qtr. | Purchasing | 4
100175 | Burgess Patricia | IV | ST - XS.PRINT.AR.STATEMENT | Open | Minor Change | 2008 - 4 Qtr. | Accounts Receivable | 4
100092 | Leung Laurence | II | Should not allow copying of Purchase Orders of the type Legacy when EP Live | Open | Minor Change | 2009 - 1 Qtr. | E-Procurement Lite | 4
100133 | Schmidt Philomena | II | Partial Month Pay Calculation | Open | Minor Change | 2009 - 1 Qtr. | Payroll | 4
100143 | Strayer Vicki | II | CRPFA Graduate Counts Are Low | Open | Standard Change - BF | 2009 - 1 Qtr. | Other | 4
100171 | Strayer Vicki | II | New Val Code and report Modification to accept for Aliens that change status | Open | State/Federal Reporting Change | 2009 - 1 Qtr. | Federal Reporting | 4
100187 | MacKenzie Ken | II | Detailing into Non-AR Receipt Code allows this field to populate | Open | Minor Change | 2009 - 1 Qtr. | Accounts Receivable | 4
100211 | Burgess Patricia | II | URR - Add the student’s telephone | Open | Minor Change | 2009 - 1 Qtr. | Financial Aid | 4
100215 | Shillu Joseph | II | ST-XSDF-Can a report by generated by AR types for the setoff debt report | Open | Minor Change | 2009 - 1 Qtr. | Accounts Receivable | 4
100217 | MacKenzie Ken | II | XCRA - Voided checks not appearing on report | Open | Minor Change | 2009 - 1 Qtr. | Financial Aid | 4
100306 | Pickett Angelica | II | XCVR Verification Report Errors - Report numbers 9 & 11 | Open | Standard Change - BF | 2009 - 1 Qtr. | Accounts Receivable | 4
100321 | MacKenzie Ken | II | ST - XORR - Report includes no detail lines and no balance | Open | Standard Change - BF | 2009 - 1 Qtr. | Accounts Receivable | 4
100119 | Pickett Angelica | III | Problem Executing XARS Report | Open | Standard Change - BF | 2009 - 1 Qtr. | Other | 4
100148 | Cooper Catherine | III | CF-Safety-XSEM-Missing 2 valcode tables called XSF.REPORT.CODE and XSF.SIC | Open | Standard Change - BF | 2009 - 1 Qtr. | Safety | 4
100154 | Schmidt Philomena | III | HR- XLRR Leave Register Report change/addition | Open | Minor Change | 2009 - 1 Qtr. | Payroll | 4
100270 | Strayer Vicki | III | Custom computed columns include academic level of "UG" and don't work | Open | Standard Change - BF | 2009 - 1 Qtr. | Other | 4
100320 | Ridl Kathy | III | CF - XIFR - Institutional Funds Report, Uninitalized Variable error and missing help | Open | Standard Change - BF | 2009 - 1 Qtr. | General Ledger | 4
100051 | Tai-Rowlands Kathy | IV | Track Contract Approvals | Open | Major Change | 2009 - 1 Qtr. | Other | 4
100056 | Goff Cinda | IV | Datatel Active Campus Portal Rollout | Open | New System/Application | 2009 - 1 Qtr. | UI Web | 4
100078 | Strayer Vicki | IV | ST - Drop/Add Request | Open | Datatel Minor Release Change | 2009 - 1 Qtr. | Registration | 4
100084 | Leung Laurence | IV | E-Procurement recycled field not being updated every time. | Open | Standard Change - BF | 2009 - 1 Qtr. | E-Procurement Lite | 4
100087 | Ridl Kathy | IV | XXGE Change to GL Summary Portion | Open | Minor Change | 2009 - 1 Qtr. | General Ledger | 4
100096 | Gilchrist Danny | IV | Cannot set field level security for fields defined in a higher level application | Open | Standard Change - BF | 2009 - 1 Qtr. | Other | 4
100107 | Strayer Vicki | IV | Proration By Major (Possible change to Acad Program Start Date) | Open | Major Change | 2009 - 1 Qtr. | Academic Records | 4
100153 | Tai-Rowlands Kathy | IV | XDBR - voc code does display in the account number but regardless of the month chosen in this fiscal year you get the budget that is currently in colleague - Cape Fear | Open | Major Change | 2009 - 1 Qtr. | Budget Management | 4
100156 | Shillu Joseph | IV | ARDE - new functionality related to convenience fees | Open | Major Change | 2009 - 1 Qtr. | Accounts Receivable | 4
100176 | Burgess Patricia | IV | User would like option to enter individual IDs to print label on FAFL | Open | Minor Change | 2009 - 1 Qtr. | Financial Aid | 4
100213 | Strayer Vicki | IV | ST - SOFF - Conflicts alert dialog box, requesting a change in message | Open | Minor Change | 2009 - 1 Qtr. | Registration | 4
100263 | Gilchrist Danny | IV | HR - XLRR - Four bugs discoved during R18 Testing | Open | Standard Change - BF | 2009 - 1 Qtr. | Personnel | 4
100012 | Maxie Duane | II | E-Pay for Payroll & Sales Tax | Open | State/Federal Reporting Change | 2009 - 2 Qtr. | Other | 4
100035 | Sawyer George | II | ST - TRCL - Doesn't display CE course work | Open | Standard Change - BF | 2009 - 2 Qtr. | Academic Records | 4
100036 | Shillu Joseph | II | GTCC Performance Issues | Open | Standard Change - BF | 2009 - 2 Qtr. | Other | 4
100089 | Maxie Duane | II | Accurate Employee Counts - Rewritten as an Envision Process - Previously XOMB | Open | Minor Change | 2009 - 2 Qtr. | Personnel | 4
100118 | Strayer Vicki | II | ST-XPAF-Guilford-Report not pulling correct data | Open | Standard Change - BF | 2009 - 2 Qtr. | Program Audit | 4
100132 | Schmidt Philomena | II | WebAdvisor Time Entry and Approval--Overtime Subroutine Requirements | Open | Minor Change | 2009 - 2 Qtr. | Payroll | 4
100181 | Shillu Joseph | II | Enhance the CIS software to provide an automated interface with the College Foundation, Inc. (CFI) | Open | Major Change | 2009 - 2 Qtr. | Financial Aid | 4
100060 | Strayer Vicki | III | ST - XATR - Roster Alignment problem | Open | Minor Change | 2009 - 2 Qtr. | Other | 4
100091 | Leung Laurence | III | Unable to determine EP vendor's remittance address differences in Colleague | Open | Minor Change | 2009 - 2 Qtr. | E-Procurement Lite | 4
100094 | Leung Laurence | III | VOUM - Voucher Type missing valcode menu options | Open | Standard Change - BF | 2009 - 2 Qtr. | E-Procurement Lite | 4
100100 | Ridl Kathy | III | XIFR and XDBR unit number sort selection for active accounts | Open | Minor Change | 2009 - 2 Qtr. | General Ledger | 4
100150 | Strayer Vicki | III | ST - XFTE (XSTF001) process obsoleted back in 2003 but was migrated to R18 | Open | Minor Change | 2009 - 2 Qtr. | State/Provincial Reporting | 4
100159 | Ridl Kathy | III | Fixed Asset maintenance - Request for field modification for disposal date and disposal fund sources | Open | Minor Change | 2009 - 2 Qtr. | Fixed Assets | 4
100182 | Strayer Vicki | III | XATR - Change request for XATR | Open | Minor Change | 2009 - 2 Qtr. | Other | 4
100082 | Strayer Vicki | IV | XCSS - Student Statistical Report - Not reporting immured students | Open | Standard Change - BF | 2009 - 2 Qtr. | Academic Records | 4
100126 | Ridl Kathy | IV | Spec for AP Single Voucher Flag Processing | Open | Minor Change | 2009 - 2 Qtr. | Purchasing | 4
100147 | Cooper Catherine | IV | Problems with Work Orders via Web Advisor - WORE | Open | Standard Change - BF | 2009 - 2 Qtr. | Physical Plant | 4
100155 | Tai-Rowlands Kathy | IV | CF - Users Want Reports To Use Record Security | Open | Minor Change | 2009 - 2 Qtr. | Other | 4
100203 | MacKenzie Ken | IV | SPSP and SPSR - Problem with Data coming out of Colleague needed for printed form | Open | Major Change | 2009 - 2 Qtr. | Accounts Receivable | 4
100264 | MacKenzie Ken | IV | ST - XXCB - Process and field help script error | Open | Minor Change | 2009 - 2 Qtr. | Cash Receipts | 4
100265 | MacKenzie Ken | IV | ST - XXCR - field help incorrect/missing for Beginning Deposit Number and Ending Deposit Number fields | Open | Minor Change | 2009 - 2 Qtr. | Cash Receipts | 4
100123 | Shillu Joseph | II | Perkins Reporting Changes | Open | State/Federal Reporting Change | 2009 - 3 Qtr. | Federal Reporting | 4
100011 | Maxie Duane | III | HR - Obsolete XHRF Retirement File Process | Open | Standard Change - BF | 2009 - 3 Qtr. | Other | 4
100040 | Leung Laurence | III | CF - POEM Requesting change in print order | Open | Minor Change | 2009 - 3 Qtr. | Purchasing | 4
100065 | Maxie Duane | III | HR - TRMW not printing the complete warning msg | Open | Standard Change - BF | 2009 - 3 Qtr. | Personnel | 4
100097 | Leung Laurence | III | CF-VOUM-CENTRAL CAROLINA- Problems entering Freight commodity code | Open | Standard Change - BF | 2009 - 3 Qtr. | E-Procurement Lite | 4
100185 | Strayer Vicki | III | COA - Request for Cumulative Totals for GPA on Transcript | Open | Minor Change | 2009 - 3 Qtr. | Other | 4
100218 | Strayer Vicki | III | ST - Obsolete mnemonics from HDR module | Open | Standard Change - BF | 2009 - 3 Qtr. | Other | 4
100239 | Strayer Vicki | III | Webadvisor address display shows 3 lines, yet transcript subroutine only displays 2 line | Open | Minor Change | 2009 - 3 Qtr. | Academic Records | 4
100149 | Cooper Catherine | IV | CF - Can Work Order requests be filtered by campus ? – Caldwell | Open | Minor Change | 2009 - 3 Qtr. | Physical Plant | 4
100152 | Cooper Catherine | IV | XIIR should allow for multiple runs in a given annual inventory period | Open | Major Change | 2009 - 3 Qtr. | Inventory | 4
100163 | Ridl Kathy | IV | 1099 Processing Box 18 | Open | Minor Change | 2009 - 3 Qtr. | Other | 4
100210 | Strayer Vicki | IV | GRDS - Additional Option to see number of students per grade | Open | Minor Change | 2009 - 3 Qtr. | Academic Records | 4
100227 | Leung Laurence | IV | Update the NIGP Commodity Code Listing on the E-Procurement Website | Open | Control Setting | 2009 - 3 Qtr. | E-Procurement Lite | 4
100238 | Strayer Vicki | IV | ST - Record lock if more than one person accesses STPE, "ST.PARMS XOB.DEFAULT locked by user...." | Open | Standard Change - BF | 2009 - 3 Qtr. | Registration | 4
100268 | Gilchrist Danny | IV | CF - XXGE - request for purchase order number and it's associated GL number to align on report | Open | Minor Change | 2009 - 3 Qtr. | Accounts Payable | 4
100109 | Strayer Vicki | II | Continuing Education ICR Report File Layout Changes | Open | State/Federal Reporting Change | 2009 - 4 Qtr. | State/Provincial Reporting | 4
100116 | Strayer Vicki | II | ST CRPFA Report needs Hours in Major set to correct fields | Open | Standard Change - BF | 2009 - 4 Qtr. | State/Provincial Reporting | 4
100173 | Strayer Vicki | II | Request to add Student ID on RGPE | Open | Standard Change - BF | 2009 - 4 Qtr. | Other | 4
100103 | Maxie Duane | IV | System Office Personnel Applicant Module | Open | New System/Application | 2009 - 4 Qtr. | Other | 4
100158 | Leung Laurence | IV | Part numbers from catalog punch-out are not printing on Purchase Orders | Open | Minor Change | 2009 - 4 Qtr. | E-Procurement Lite | 4
100180 | Gilchrist Danny | IV | Request for Comparing Fields On RMSM Screen To Facilities Room Characteristic Report | Open | Minor Change | 2009 - 4 Qtr. | Other | 4