Trinity Creeks’ Block Party 2018 summary

THE NUMBERS:

- Total attendance – 102

- Paid and no show – 10

FINANCIAL SUMMARY:

- Approximately $146 deficit

WHAT WENT WELL:

- Great work of the committee, board, and volunteers

- Dedication of monumental sign

- Excess food donated to Rich Township Food Pantry

- Overall an enjoyable day for many

- Additional side dishes contributed

- Great music from “DJ” Kevin and family

- The use of easy “pop-up” tents limited manpower needed at setup

- Approximate $60 received from 50/50 raffle

- Many local politicians attended, including Village President Sheila Chalmers-Currin

- A wide variety of games

- Fire Department demonstration

- Bugs were not a problem

- Camaraderie among attendees

- Revised registration system worked well; moving registration to middle of the block was a success

- Using Marilyn’s house as a base worked well

WHAT DID NOT GO WELL:

- Ten families who were unable to participate after paying

- Overall attendance was down

- Great effort by committee for lessor results

- Some did not understand who had tee shirts

- Game truck may be too expensive

RECOMMENDATIONS TO THE BOARD:

- No block party for 2019, but “Old fashioned backyard BBQ” for those residents interested starting in 2019, with a decision on 2020 to be made later

- Plan holiday gathering for those residents interested at local restaurant

Judson Mitchell, Chair; Geri Morris; Marilyn Stewart; Marvin Ruffin; Liz Ruffin; Kevin Richard; Carmen Richard

August 27, 2018